## OsoBio (hidden)
PO # | WO # | Site | Lot # | Lot Size | SD Hydration | Fill Date | Unload Date | Planned CMO Release | Planned Gilead QA release | Planned Ship | Destination | Market | WO Status | Comments
801352182 | 40200190 | OsoBio | GAD123 | 35000 | 2018-09-28 | 2018-10-06 | 2018-10-09 | 2018-11-08 | 2018-11-29 | 2018-12-06 | Cork | EU | Completed
801352183 | 40200191 | OsoBio | GAD124 | 35000 | 2018-10-02 | 2018-10-11 | 2018-10-14 | 2018-11-13 | 2018-12-04 | 2018-12-11 | San Dimas | US | Completed
801352184 | 40200192 | OsoBio | GAD125 | 35000 | 2018-10-04 | 2018-10-16 | 2018-10-19 | 2018-11-18 | 2018-12-09 | 2018-12-16 | Cork | EU | Completed
801352185 | 40200193 | OsoBio | GAD126 | 35000 | 2018-10-12 | 2018-10-20 | 2018-10-23 | 2018-11-22 | 2018-12-13 | 2018-12-20 | Cork | EU | Completed
801352186 | 40200194 | OsoBio | GAD127 | 35000 | 2018-10-19 | 2018-10-26 | 2018-10-29 | 2018-11-28 | 2018-12-19 | 2018-12-26 | Cork | EU | Completed
801352196 | 40200199 | OsoBio | GAD132 | 35000 | 2018-11-12 | 2018-11-25 | 2018-11-28 | 2018-12-28 | 2019-01-18 | 2018-12-28 | Cork | EU | Completed
801352197 | 40200200 | OsoBio | GAD133 | 35000 | 2018-11-16 | 2018-11-28 | 2018-12-01 | 2018-12-31 | 2019-01-21 | 2018-12-28 | Cork | EU | Completed
801352187 | 40200195 | OsoBio | GAD128 | 35000 | 2018-10-28 | 2018-11-02 | 2018-11-05 | 2018-12-05 | 2018-12-26 | 2019-01-02 | Cork | EU | Completed
801352188 | 40200196 | OsoBio | GAD129 | 35000 | 2018-11-01 | 2018-11-08 | 2018-11-11 | 2018-12-11 | 2019-01-01 | 2019-01-08 | Cork | EU | Completed
801369809 | 40200166 | OsoBio | GAD108 | 35000 | 2018-08-03 | 2018-08-09 | 2018-08-12 | 2018-12-09 | 2018-12-30 | 2019-01-09 | SD | US | Completed
801352193 | 40200197 | OsoBio | GAD130 | 35000 | 2018-11-03 | 2018-11-14 | 2018-11-17 | 2018-12-17 | 2019-01-07 | 2019-01-14 | San Dimas | Australia / New Zealand / Colombia - 29000/6000 | Completed
801352194 | 40200198 | OsoBio | GAD131 | 35000 | 2018-11-06 | 2018-11-17 | 2018-11-20 | 2018-12-20 | 2019-01-10 | 2019-01-17 | San Dimas | US | Completed
801352175 | 40200187 | OsoBio | GAD120 | 35000 | 2018-09-16 | 2018-09-27 | 2018-09-30 | 2018-11-02 | 2018-11-23 | 2018-11-30 | SD | US | WIP | Multiple deviation - EM hit, Technician exceeded time limit, power loss. Target closure for this deviation is within the next 3 weeks (by 8Feb2019). Once closed Oso will upload batch so our QA can review and release for shipment. Target release will be 15Feb2019.
801352198 | 40200201 | OsoBio | GAD134 | 35000 | 2018-11-20 | 2018-12-03 | 2018-12-06 | 2019-01-05 | 2019-01-26 | 2019-01-09 | San Dimas | US | WIP | Internal deviation. Samples needed. Samples taken and will ship to san dimas to test. Will receive in SD to do testing feb 1… Target closure date for internal deviation is 11feb2019.
801352199 | 40200202 | OsoBio | GAD135 | 35000 | 2018-11-30 | 2018-12-05 | 2018-12-08 | 2019-01-07 | 2019-01-28 | 2019-02-04 | Cork | EU | Completed
801352092 | 40200181 | OsoBio | GAD136 | 35000 | 2018-12-04 | 2018-12-08 | 2018-12-11 | 2019-01-10 | 2019-01-31 | 2019-02-07 | Cork | EU | WIP | This lot has failed testing at San Dimas. Will be rejected.
801352096 | 40200182 | OsoBio | GAD137 | 35000 | 2018-12-06 | 2018-12-11 | 2018-12-14 | 2019-01-13 | 2019-02-03 | 2019-02-08 | Cork | EU | WIP | This lot will be shipping Friday for a delivery to cork on 11Jan2019.
801352098 | 40200183 | OsoBio | GAD138 | 35000 | 2019-01-20 | 2019-01-26 | 2019-01-29 | 2019-02-28 | 2019-03-21 | 2019-03-28 | Cork | EU | Pending
801369819 | 40200173 | OsoBio | GAD139 | 35000 | 2019-01-22 | 2019-01-28 | 2019-01-31 | 2019-03-02 | 2019-03-23 | 2019-03-30 | Cork | EU | Pending | Stability batch.
801369820 | 40200174 | OsoBio | GAD140 | 35000 | 2019-01-28 | 2019-02-01 | 2019-02-04 | 2019-03-06 | 2019-03-27 | 2019-04-03 | Cork | EU | Pending
801369821 | 40200175 | OsoBio | GAD141 | 35000 | 2019-01-30 | 2019-02-04 | 2019-02-07 | 2019-03-09 | 2019-03-30 | 2019-04-06 | Cork | EU | Pending
801369823 | 40200176 | OsoBio | GAD142 | 35000 | 2019-02-04 | 2019-02-08 | 2019-02-11 | 2019-03-13 | 2019-04-03 | 2019-04-10 | Cork | EU | Pending
801369825 | 40200177 | OsoBio | GAD143 | 35000 | 2019-02-07 | 2019-02-10 | 2019-02-13 | 2019-03-15 | 2019-04-05 | 2019-04-12 | Cork | EU | Pending
801369827 | 40200178 | OsoBio | GAD144 | 35000 | 2019-02-11 | 2019-02-14 | 2019-02-17 | 2019-03-19 | 2019-04-09 | 2019-04-16 | Cork | EU | Pending
801373409 | 40200203 | OsoBio | GAD145 | 35000 | 2019-02-12 | 2019-02-16 | 2019-02-19 | 2019-03-21 | 2019-04-11 | 2019-04-18 | Cork | EU | Pending
801373410 | 40200204 | OsoBio | GAD146 | 35000 | 2019-02-15 | 2019-02-19 | 2019-02-22 | 2019-03-24 | 2019-04-14 | 2019-04-21 | Cork | EU | Pending
801373411 | 40200205 | OsoBio | GAD147 | 35000 | 2019-02-18 | 2019-02-21 | 2019-02-24 | 2019-03-26 | 2019-04-16 | 2019-04-23 | Cork | EU | Pending
801375898 | 40200206 | OsoBio | GAD148 | 35000 | 2019-02-19 | 2019-02-24 | 2019-02-27 | 2019-03-29 | 2019-04-19 | 2019-04-26 | Cork | EU | Pending
801380735 | 40200207 | OsoBio | GAD149 | 35000 | 2019-02-22 | 2019-02-26 | 2019-03-01 | 2019-03-31 | 2019-04-21 | 2019-04-28 | Cork | EU | Pending
801380737 | 40200208 | OsoBio | GAD150 | 35000 | 2019-02-25 | 2019-03-01 | 2019-03-04 | 2019-04-03 | 2019-04-24 | 2019-05-01 | Cork | EU | Pending
801380738 | 40200209 | OsoBio | GAD151 | 35000 | 2019-02-26 | 2019-03-03 | 2019-03-06 | 2019-04-05 | 2019-04-26 | 2019-05-03 | Cork | EU | Pending
801380739 | 40200210 | OsoBio | GAD152 | 35000 | 2019-02-28 | 2019-03-06 | 2019-03-09 | 2019-04-08 | 2019-04-29 | 2019-05-06 | Cork | EU | Pending
801380740 | 40200211 | OsoBio | GAD153 | 35000 | 2019-03-01 | 2019-03-08 | 2019-03-11 | 2019-04-10 | 2019-05-01 | 2019-05-08 | Cork | EU | Pending
801380741 | 40200212 | OsoBio | GAD154 | 35000 | 2019-03-04 | 2019-03-11 | 2019-03-14 | 2019-04-13 | 2019-05-04 | 2019-05-11 | San Dimas | Australia / New Zealand / Colombia - 20000/15000 | Pending
801380742 | 40200213 | OsoBio | GAD155 | 35000 | 2019-03-05 | 2019-03-14 | 2019-03-17 | 2019-04-16 | 2019-05-07 | 2019-05-14 | Cork | EU | Pending
801380743 | 40200214 | OsoBio | GAD156 | 35000 | 2019-03-11 | 2019-03-17 | 2019-03-20 | 2019-04-19 | 2019-05-10 | 2019-05-17 | Cork | EU | Pending
801386686 |  | OsoBio |  | 35000 | 2019-03-12 | 2019-03-19 | 2019-03-22 | 2019-04-21 | 2019-05-12 | 2019-05-19 | Cork | EU
801386687 |  | OsoBio |  | 35000 | 2019-03-14 | 2019-03-22 | 2019-03-25 | 2019-04-24 | 2019-05-15 | 2019-05-22 | Cork | EU
801386689 |  | OsoBio |  | 35000 | 2019-03-15 | 2019-03-24 | 2019-03-27 | 2019-04-26 | 2019-05-17 | 2019-05-24 | Cork | EU
801386690 |  | OsoBio |  | 35000 | 2019-03-18 | 2019-03-27 | 2019-03-30 | 2019-04-29 | 2019-05-20 | 2019-05-27 | Cork | EU
801386691 |  | OsoBio |  | 35000 | 2019-03-22 | 2019-04-01 | 2019-04-04 | 2019-05-04 | 2019-05-25 | 2019-06-01 | Cork | EU
801386694 |  | OsoBio |  | 35000 | 2019-03-26 | 2019-04-04 | 2019-04-07 | 2019-05-07 | 2019-05-28 | 2019-06-04 | San Dimas | Brazil Access
801386696 |  | OsoBio |  | 35000 | 2019-03-29 | 2019-04-06 | 2019-04-09 | 2019-05-09 | 2019-05-30 | 2019-06-06 | San Dimas | Brazil Access
801386698 |  | OsoBio |  | 35000 | 2019-04-02 | 2019-04-10 | 2019-04-13 | 2019-05-13 | 2019-06-03 | 2019-06-10 | Cork | EU
801386699 |  | OsoBio |  | 35000 | 2019-04-04 | 2019-04-11 | 2019-04-14 | 2019-05-14 | 2019-06-04 | 2019-06-11 | Cork | EU
801386700 |  | OsoBio |  | 35000 | 2019-04-12 | 2019-04-19 | 2019-04-22 | 2019-05-22 | 2019-06-12 | 2019-06-19 | Cork | EU
801386701 |  | OsoBio |  | 35000 | 2019-04-16 | 2019-04-24 | 2019-04-27 | 2019-05-27 | 2019-06-17 | 2019-06-24 | Cork | EU
801386705 |  | OsoBio |  | 35000 | 2019-04-18 | 2019-04-26 | 2019-04-29 | 2019-05-29 | 2019-06-19 | 2019-06-26 | Cork | EU
801386706 |  | OsoBio |  | 35000 | 2019-04-22 | 2019-05-02 | 2019-05-05 | 2019-06-04 | 2019-06-25 | 2019-07-02 | Cork | EU
801390244 |  | OsoBio |  | 35000 | 2019-04-25 | 2019-05-04 | 2019-05-07 | 2019-06-06 | 2019-06-27 | 2019-07-04 | Cork | EU
801390245 |  | OsoBio |  | 35000 | 2019-04-30 | 2019-05-08 | 2019-05-11 | 2019-06-10 | 2019-07-01 | 2019-07-08 | Cork | EU
801390246 |  | OsoBio |  | 35000 | 2019-05-02 | 2019-05-09 | 2019-05-12 | 2019-06-11 | 2019-07-02 | 2019-07-09 | San Dimas | Australia / New Zealand
801390247 |  | OsoBio |  | 35000 | 2019-05-07 | 2019-05-15 | 2019-05-18 | 2019-06-17 | 2019-07-08 | 2019-07-15 | Cork | EU
801390248 |  | OsoBio |  | 35000 | 2019-05-10 | 2019-05-17 | 2019-05-20 | 2019-06-19 | 2019-07-10 | 2019-07-17 | Cork | EU
801390249 |  | OsoBio |  | 35000 | 2019-05-14 | 2019-05-20 | 2019-05-23 | 2019-06-22 | 2019-07-13 | 2019-07-20 | Cork | EU
|  | OsoBio |  | 35000 | 2019-05-21 | 2019-05-28 | 2019-05-31 | 2019-06-30 | 2019-07-21 | 2019-07-28 | Cork | EU
|  | OsoBio |  | 35000 | 2019-05-24 | 2019-05-30 | 2019-06-02 | 2019-07-02 | 2019-07-23 | 2019-07-30 | Cork | EU
|  | OsoBio |  | 35000 | 2019-05-30 | 2019-06-06 | 2019-06-09 | 2019-07-09 | 2019-07-30 | 2019-08-06 | Cork | EU
|  | OsoBio |  | 35000 | 2019-05-31 | 2019-06-07 | 2019-06-10 | 2019-07-10 | 2019-07-31 | 2019-08-07 | Cork | EU
|  | OsoBio |  | 35000 | 2019-06-04 | 2019-06-11 | 2019-06-14 | 2019-07-14 | 2019-08-04 | 2019-08-11 | Cork | EU
|  | OsoBio |  | 35000 | 2019-06-10 | 2019-06-15 | 2019-06-18 | 2019-07-18 | 2019-08-08 | 2019-08-15 | Cork | EU
|  | OsoBio |  | 35000 | 2019-07-19 | 2019-07-27 | 2019-07-30 | 2019-08-29 | 2019-09-19 | 2019-09-26 | Cork | EU
|  | OsoBio |  | 35000 | 2019-07-25 | 2019-07-31 | 2019-08-03 | 2019-09-02 | 2019-09-23 | 2019-09-30 | Cork | EU
|  | OsoBio |  | 35000 | 2019-07-26 | 2019-08-02 | 2019-08-05 | 2019-09-04 | 2019-09-25 | 2019-10-02 | Cork | EU
|  | OsoBio |  | 35000 | 2019-08-01 | 2019-08-07 | 2019-08-10 | 2019-09-09 | 2019-09-30 | 2019-10-07 | Cork | EU
|  | OsoBio |  | 35000 | 2019-08-02 | 2019-08-08 | 2019-08-11 | 2019-09-10 | 2019-10-01 | 2019-10-08 | San Dimas | Australia / New Zealand
|  | OsoBio |  | 35000 | 2019-08-08 | 2019-08-15 | 2019-08-18 | 2019-09-17 | 2019-10-08 | 2019-10-15 | Cork | EU
|  | OsoBio |  | 35000 | 2019-08-12 | 2019-08-18 | 2019-08-21 | 2019-09-20 | 2019-10-11 | 2019-10-18 | Cork | EU
|  | OsoBio |  | 35000 | 2019-08-16 | 2019-08-23 | 2019-08-26 | 2019-09-25 | 2019-10-16 | 2019-10-23 | Cork | EU
|  | OsoBio |  | 35000 | 2019-08-19 | 2019-08-26 | 2019-08-29 | 2019-09-28 | 2019-10-19 | 2019-10-26 | Cork | EU
|  | OsoBio |  | 35000 | 2019-08-22 | 2019-08-28 | 2019-08-31 | 2019-09-30 | 2019-10-21 | 2019-10-28 | Cork | EU
|  | OsoBio |  | 35000 | 2019-08-26 | 2019-09-04 | 2019-09-07 | 2019-10-07 | 2019-10-28 | 2019-11-04 | San Dimas | Brazil Access
|  | OsoBio |  | 35000 | 2019-08-30 | 2019-09-07 | 2019-09-10 | 2019-10-10 | 2019-10-31 | 2019-11-07 | San Dimas | Brazil Access
|  | OsoBio |  | 35000 | 2019-09-03 | 2019-09-09 | 2019-09-12 | 2019-10-12 | 2019-11-02 | 2019-11-09 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-05 | 2019-09-12 | 2019-09-15 | 2019-10-15 | 2019-11-05 | 2019-11-12 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-09 | 2019-09-14 | 2019-09-17 | 2019-10-17 | 2019-11-07 | 2019-11-14 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-12 | 2019-09-18 | 2019-09-21 | 2019-10-21 | 2019-11-11 | 2019-11-18 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-13 | 2019-09-19 | 2019-09-22 | 2019-10-22 | 2019-11-12 | 2019-11-19 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-17 | 2019-09-23 | 2019-09-26 | 2019-10-26 | 2019-11-16 | 2019-11-23 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-20 | 2019-09-25 | 2019-09-28 | 2019-10-28 | 2019-11-18 | 2019-11-25 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-23 | 2019-09-28 | 2019-10-01 | 2019-10-31 | 2019-11-21 | 2019-11-28 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-26 | 2019-10-02 | 2019-10-05 | 2019-11-04 | 2019-11-25 | 2019-12-02 | Cork | EU
|  | OsoBio |  | 35000 | 2019-09-27 | 2019-10-04 | 2019-10-07 | 2019-11-06 | 2019-11-27 | 2019-12-04 | Cork | EU
|  | OsoBio |  | 35000 | 2019-10-03 | 2019-10-10 | 2019-10-13 | 2019-11-12 | 2019-12-03 | 2019-12-10 | Cork | EU
|  | OsoBio |  | 35000 | 2019-10-07 | 2019-10-13 | 2019-10-16 | 2019-11-15 | 2019-12-06 | 2019-12-13 | Cork | EU
|  | OsoBio |  | 35000 | 2019-10-08 | 2019-10-15 | 2019-10-18 | 2019-11-17 | 2019-12-08 | 2019-12-15 | Cork | EU
|  | OsoBio |  | 35000 | 2019-10-11 | 2019-10-18 | 2019-10-21 | 2019-11-20 | 2019-12-11 | 2019-12-18 | Cork | EU
|  | OsoBio |  | 35000 | 2019-10-17 | 2019-10-23 | 2019-10-26 | 2019-11-25 | 2019-12-16 | 2019-12-23 | Cork | EU
|  | OsoBio |  | 35000 | 2019-10-24 | 2019-10-30 | 2019-11-02 | 2019-12-02 | 2019-12-23 | 2019-12-30 | Cork | EU
|  | OsoBio |  | 35000 | 2019-10-25 | 2019-11-01 | 2019-11-04 | 2019-12-04 | 2019-12-25 | 2020-01-01 | Cork | EU
|  | OsoBio |  | 35000 | 2019-11-01 | 2019-11-08 | 2019-11-11 | 2019-12-11 | 2020-01-01 | 2020-01-08 | Cork | EU
|  | OsoBio |  | 35000 | 2019-11-05 | 2019-11-11 | 2019-11-14 | 2019-12-14 | 2020-01-04 | 2020-01-11 | Cork | EU
|  | OsoBio |  | 35000 | 2019-11-07 | 2019-11-14 | 2019-11-17 | 2019-12-17 | 2020-01-07 | 2020-01-14 | Cork | EU
|  | OsoBio |  | 35000 | 2019-11-22 | 2019-12-01 | 2019-12-04 | 2020-01-03 | 2020-01-24 | 2020-01-31 | Cork | EU
|  | OsoBio |  | 35000 | 2019-11-25 | 2019-12-02 | 2019-12-05 | 2020-01-04 | 2020-01-25 | 2020-02-01 | Cork | EU
|  | OsoBio |  | 35000 | 2019-11-28 | 2019-12-06 | 2019-12-09 | 2020-01-08 | 2020-01-29 | 2020-02-05 | Cork | EU

## JHS (hidden)
PO # | WO # | Site | Lot # | Lot Size | SD Hydration | Fill Date | Unload Date | Planned CMO Release | Planned Gilead QA release | Planned Ship | Destination | Market | WO Status | Comments
801344036 | 314000251 | JHS | D1800127 | 40000 | 2018-08-18 | 2018-08-22 | 2018-08-27 | 2018-10-29 | 2018-11-19 | 2018-11-26 | San Dimas | Japan | Completed
801355874 | 314000253 | JHS | D1800152 | 40000 | 2018-10-07 | 2018-10-19 | 2018-10-24 | 2019-01-25 | 2019-02-15 | 2019-02-08 | Cork | EU | WIP | 2/5: ATS on 6Feb2019. Shipping on 8feb2019 to Cork. Delivery on Monday.
801355875 | 314000254 | JHS | D1800153 | 40000 | 2018-10-10 | 2018-10-20 | 2018-10-25 | 2018-12-19 | 2019-01-09 | 2019-01-16 | Cork | EU | Reject | Open Deviation. Planned CMO release date changed to 12/17…. This will most likely be rejected…
801355876 | 314000255 | JHS | D1800154 | 40000 | 2018-10-14 | 2018-10-24 | 2018-10-29 | 2018-12-12 | 2019-01-02 | 2018-12-28 | Cork | EU | Completed
801355883 | 314000256 | JHS | D1800204 | 40000 | 2018-10-16 | 2018-11-01 | 2018-11-06 | 2018-12-06 | 2018-12-27 | 2018-12-28 | Cork | EU | Completed
801355884 | 314000257 | JHS | D1800159 | 40000 | 2018-10-26 | 2018-11-06 | 2018-11-11 | 2019-01-23 | 2019-02-13 | 2019-02-20 | San Dimas | Japan | WIP | 2/5: PR30282: exceedd critcal allowable reject limit for loose crimps, deviation is still open. QA has provided comments, waiting on JHS to respond… deviation closure by end of this week. Target ATS will be Monday 11feb2019. SD needs to receive this lot by 15feb2019.
801355885 | 314000258 | JHS | D1800167 | 40000 | 2018-10-30 | 2018-11-13 | 2018-11-18 | 2019-01-18 | 2019-02-08 | 2019-02-06 | San Dimas | US | Completed
801344030 | 314000247 | JHS | D1800168 | 40000 | 2018-11-08 | 2018-11-16 | 2018-11-21 | 2019-01-16 | 2019-02-06 | 2019-02-08 | Cork | EU | WIP | Shipping on 8feb2019 to Cork. Delivery on Monday.
801373424 | 314000259 | JHS | D1800172 | 40000 | 2018-11-10 | 2018-11-21 | 2018-11-26 | 2019-02-13 | 2019-03-06 | 2019-03-13 | Cork | EU | WIP | 2/5: PR31556 & 32097 Multiple deviations open on this lot. Exceeded lighthouse reject rate & sterility investigation. Waiting on comments at Cork. Deviations will target to close by 11Feb2019.
801373425 | 314000260 | JHS | D1800173 | 40000 | 2018-11-14 | 2018-11-28 | 2018-12-03 | 2019-02-06 | 2019-02-27 | 2019-03-06 | San Dimas | Japan | WIP | Partial batch record uploaded. Pending QA review. PR36295. Exceeded critical reject limit.
801373427 | 314000261 | JHS | D1800174 | 40000 | 2018-11-18 | 2018-12-03 | 2018-12-08 | 2019-01-29 | 2019-02-19 | 2019-02-26 | Cork | EU | WIP | impacted by delay in lighthouse inspection. PR36295. Exceeded critical reject limit.
801373428 | 314000262 | JHS | D1800176 | 40000 | 2018-11-28 | 2018-12-06 | 2018-12-11 | 2019-02-01 | 2019-02-22 | 2019-03-01 | Cork | EU | WIP | impacted by delay in lighthouse inspection.
801373429 | 314000263 | JHS | D1800177 | 40000 | 2018-12-02 | 2018-12-11 | 2018-12-16 | 2019-02-04 | 2019-02-25 | 2019-03-04 | Cork | EU | WIP | impacted by delay in lighthouse inspection.
801373430 | 314000264 | JHS | D1800178 | 40000 | 2018-12-08 | 2018-12-14 | 2018-12-19 | 2019-02-08 | 2019-03-01 | 2019-03-08 | Cork | EU | WIP | impacted by delay in lighthouse inspection.
801355870 | 314000252 | JHS | D1900003 | 40000 | 2019-01-13 | 2019-01-16 | 2019-01-21 | 2019-03-17 | 2019-04-07 | 2019-04-14 | Cork | EU
801380403 | 314000265 | JHS | D1900004 | 40000 | 2019-01-11 | 2019-01-22 | 2019-01-27 | 2019-03-23 | 2019-04-13 | 2019-04-20 | Cork | EU |  | 2 EM deviations
801380406 | 314000266 | JHS | D1900006 | 40000 | 2019-01-18 | 2019-01-25 | 2019-01-30 | 2019-03-26 | 2019-04-16 | 2019-04-23 | Cork | EU
801394163 | 314000273 | JHS | D1900063 | 40000 | 2019-01-24 | 2019-01-28 | 2019-02-02 | 2019-03-29 | 2019-04-19 | 2019-04-26 | Cork | EU |  | Extra fill slot taken
801380407 | 314000267 | JHS | D1900007 | 40000 | 2019-01-26 | 2019-01-30 | 2019-02-04 | 2019-03-31 | 2019-04-21 | 2019-04-28 | Cork | EU
801380408 | 314000268 | JHS | D1900009 | 40000 | 2019-02-01 | 2019-02-06 | 2019-02-11 | 2019-04-07 | 2019-04-28 | 2019-05-05 | San Dimas | Japan |  | Critical deviation
801380409 | 314000269 | JHS | D1900010 | 40000 | 2019-02-05 | 2019-02-09 | 2019-02-14 | 2019-04-10 | 2019-05-01 | 2019-05-08 | San Dimas | Japan
801380410 | 314000270 | JHS | D1900011 | 40000 | 2019-02-08 | 2019-02-13 | 2019-02-18 | 2019-04-14 | 2019-05-05 | 2019-05-12 | San Dimas | Argentina
801380411 | 314000271 | JHS | D1900013 | 40000 | 2019-03-25 | 2019-04-02 | 2019-04-07 | 2019-06-01 | 2019-06-22 | 2019-06-29 | Cork | EU
801380412 | 314000272 | JHS | D1900014 | 40000 | 2019-03-28 | 2019-04-05 | 2019-04-10 | 2019-06-04 | 2019-06-25 | 2019-07-02 | Cork | EU
|  | JHS |  | 40000 | 2019-04-01 | 2019-04-10 | 2019-04-15 | 2019-06-09 | 2019-06-30 | 2019-07-07 | Cork | EU
|  | JHS |  | 40000 | 2019-04-05 | 2019-04-16 | 2019-04-21 | 2019-06-15 | 2019-07-06 | 2019-07-13 | Cork | EU
|  | JHS |  | 40000 | 2019-04-09 | 2019-04-19 | 2019-04-24 | 2019-06-18 | 2019-07-09 | 2019-07-16 | Cork | EU
|  | JHS |  | 40000 | 2019-04-15 | 2019-04-24 | 2019-04-29 | 2019-06-23 | 2019-07-14 | 2019-07-21 | Cork | EU
|  | JHS |  | 40000 | 2019-04-19 | 2019-04-30 | 2019-05-05 | 2019-06-29 | 2019-07-20 | 2019-07-27 | San Dimas | Mexico |  | may split with Argentina with Argentina demand increases
|  | JHS |  | 40000 | 2019-04-23 | 2019-05-03 | 2019-05-08 | 2019-07-02 | 2019-07-23 | 2019-07-30 | Cork | EU
|  | JHS |  | 40000 | 2019-04-29 | 2019-05-08 | 2019-05-13 | 2019-07-07 | 2019-07-28 | 2019-08-04 | San Dimas | Japan
|  | JHS |  | 40000 | 2019-05-06 | 2019-05-14 | 2019-05-19 | 2019-07-13 | 2019-08-03 | 2019-08-10 | San Dimas | Japan
|  | JHS |  | 40000 | 2019-05-09 | 2019-05-17 | 2019-05-22 | 2019-07-16 | 2019-08-06 | 2019-08-13 | Cork | EU
|  | JHS |  | 40000 | 2019-05-16 | 2019-05-22 | 2019-05-27 | 2019-07-21 | 2019-08-11 | 2019-08-18 | Cork | EU
|  | JHS |  | 40000 | 2019-05-23 | 2019-05-31 | 2019-06-05 | 2019-07-30 | 2019-08-20 | 2019-08-27 | Cork | EU
|  | JHS |  | 40000 | 2019-05-27 | 2019-06-05 | 2019-06-10 | 2019-08-04 | 2019-08-25 | 2019-09-01 | Cork | EU
|  | JHS |  | 40000 | 2019-06-03 | 2019-06-11 | 2019-06-16 | 2019-08-10 | 2019-08-31 | 2019-09-07 | Cork | EU
|  | JHS |  | 40000 | 2019-06-07 | 2019-06-14 | 2019-06-19 | 2019-08-13 | 2019-09-03 | 2019-09-10 | Cork | EU
|  | JHS |  | 40000 | 2019-06-13 | 2019-06-19 | 2019-06-24 | 2019-08-18 | 2019-09-08 | 2019-09-15 | Cork | EU
|  | JHS |  | 40000 | 2019-06-17 | 2019-06-25 | 2019-06-30 | 2019-08-24 | 2019-09-14 | 2019-09-21 | Cork | EU
|  | JHS |  | 40000 | 2019-06-18 | 2019-06-28 | 2019-07-03 | 2019-08-27 | 2019-09-17 | 2019-09-24 | San Dimas | Argentina
|  | JHS |  | 40000 | 2019-06-20 | 2019-07-03 | 2019-07-08 | 2019-09-01 | 2019-09-22 | 2019-09-29 | San Dimas | Japan
|  | JHS |  | 40000 | 2019-07-18 | 2019-07-26 | 2019-07-31 | 2019-09-24 | 2019-10-15 | 2019-10-22 | San Dimas | Japan
|  | JHS |  | 40000 | 2019-07-22 | 2019-07-31 | 2019-08-05 | 2019-09-29 | 2019-10-20 | 2019-10-27 | Cork | EU
|  | JHS |  | 40000 | 2019-07-29 | 2019-08-06 | 2019-08-11 | 2019-10-05 | 2019-10-26 | 2019-11-02 | Cork | EU
|  | JHS |  | 40000 | 2019-08-05 | 2019-08-09 | 2019-08-14 | 2019-10-08 | 2019-10-29 | 2019-11-05 | Cork | EU
|  | JHS |  | 40000 | 2019-08-09 | 2019-08-14 | 2019-08-19 | 2019-10-13 | 2019-11-03 | 2019-11-10 | Cork | EU
|  | JHS |  | 40000 | 2019-08-15 | 2019-08-20 | 2019-08-25 | 2019-10-19 | 2019-11-09 | 2019-11-16 | Cork | EU
|  | JHS |  | 40000 | 2019-09-10 | 2019-09-18 | 2019-09-23 | 2019-11-17 | 2019-12-08 | 2019-12-15 | San Dimas | Japan
|  | JHS |  | 40000 | 2019-09-16 | 2019-09-24 | 2019-09-29 | 2019-11-23 | 2019-12-14 | 2019-12-21 | San Dimas | Japan
|  | JHS |  | 40000 | 2019-09-19 | 2019-09-27 | 2019-10-02 | 2019-11-26 | 2019-12-17 | 2019-12-24 | Cork | EU
|  | JHS |  | 40000 | 2019-09-24 | 2019-10-02 | 2019-10-07 | 2019-12-01 | 2019-12-22 | 2019-12-29 | Cork | EU
|  | JHS |  | 40000 | 2019-10-01 | 2019-10-08 | 2019-10-13 | 2019-12-07 | 2019-12-28 | 2020-01-04 | Cork | EU
|  | JHS |  | 40000 | 2019-10-04 | 2019-10-11 | 2019-10-16 | 2019-12-10 | 2019-12-31 | 2020-01-07 | Cork | EU
|  | JHS |  | 40000 | 2019-10-10 | 2019-10-16 | 2019-10-21 | 2019-12-15 | 2020-01-05 | 2020-01-12 | Cork | EU
|  | JHS |  | 40000 | 2019-10-14 | 2019-10-22 | 2019-10-27 | 2019-12-21 | 2020-01-11 | 2020-01-18 | Cork | EU
|  | JHS |  | 40000 | 2019-10-18 | 2019-10-25 | 2019-10-30 | 2019-12-24 | 2020-01-14 | 2020-01-21 | Cork | EU
|  | JHS |  | 40000 | 2019-10-21 | 2019-10-30 | 2019-11-04 | 2019-12-29 | 2020-01-19 | 2020-01-26 | Cork | EU
|  | JHS |  | 40000 | 2019-10-28 | 2019-11-05 | 2019-11-10 | 2020-01-04 | 2020-01-25 | 2020-02-01 | Cork | EU
|  | JHS |  | 40000 | 2019-11-04 | 2019-11-08 | 2019-11-13 | 2020-01-07 | 2020-01-28 | 2020-02-04 | Cork | EU
|  | JHS |  | 40000 | 2019-11-08 | 2019-11-13 | 2019-11-18 | 2020-01-12 | 2020-02-02 | 2020-02-09 | Cork | EU
|  | JHS |  | 40000 | 2019-11-11 | 2019-11-19 | 2019-11-24 | 2020-01-18 | 2020-02-08 | 2020-02-15 | Cork | EU
|  | JHS |  | 40000 | 2019-11-14 | 2019-11-22 | 2019-11-27 | 2020-01-21 | 2020-02-11 | 2020-02-18 | Cork | EU
|  | JHS |  | 40000 | 2019-11-18 | 2019-11-27 | 2019-12-02 | 2020-01-26 | 2020-02-16 | 2020-02-23 | Cork | EU
|  | JHS |  | 40000 | 2019-11-26 | 2019-12-03 | 2019-12-08 | 2020-02-01 | 2020-02-22 | 2020-02-29 | Cork | EU
|  | JHS |  | 40000 | 2019-11-29 | 2019-12-06 | 2019-12-11 | 2020-02-04 | 2020-02-25 | 2020-03-03 | Cork | EU
|  | JHS |  | 40000 | 2019-12-05 | 2019-12-11 | 2019-12-16 | 2020-02-09 | 2020-03-01 | 2020-03-08 | Cork | EU
|  | JHS |  | 40000 | 2019-12-12 | 2019-12-17 | 2019-12-22 | 2020-02-15 | 2020-03-07 | 2020-03-14 | Cork | EU
|  | JHS |  | 40000 | 2019-12-13 | 2019-12-20 | 2019-12-25 | 2020-02-18 | 2020-03-10 | 2020-03-17 | Cork | EU

## All Sites
[9 empty] | 1900-01-02 | 1900-01-03 | 1900-01-03 | 1900-01-05 | 1900-01-13 | 1900-01-14 | 1900-01-17 | 1900-01-18 | 1900-01-18 | 1900-01-15 | 1900-01-19 | 1900-01-17 | 1900-01-27 | 1900-01-18 | List Below | List Below | 1900-01-19 | 1900-01-20 |  |  | 18
[23 empty] | Cork | Clinical
[23 empty] | PCI | EUA
[23 empty] | La Verne | Commercial
[6 empty] | API Delivered to CMO | API available at CMO |  | Days in Lyo | Based onCap date | Based on Cap date | Based on Analytical sample ship date | Based on sterility samples pull annd test start | Based on Visual inspection completion | Based on Prep and arrange shipment | Based sterility samples pulled and start test | Based sterility samples pulled and start test | Based on Analytical transport and receipt | Based Analytical report to CMO | Based on Analytical samples pulled and shipped | Based on visual inspection complete | Based on Ship under Q and Receipt at Destination |  |  | Based on reciept date | Based on Pack and Label completion
[7 empty] | -1 |  | 3 | 1 | 1 | 2 | 10 - US; 8 - EU | 1 | 3 - US; 5 - EU | 15 | 15 | 10 | 4 | 14 | 10 | 1 |  |  | US - 1; EU 2 | 1 |  | 1
Angela/Zong | Angela/Zong | Angela/Zong | Angela/Zong | Angela/Zong | Angela/Zong | Jan-Ivan | Angela/Zong | Angela/Zong | Angela/Zong | Angela/Zong | Angela/Zong | Garry/Quan | Angela/Zong | Jeff Perata and Angela/Zong for updates | Jeff Perata and Angela/Zong for updates | Angela/Zong | Angela/Zong | Garry/Quan | Garry/Quan | Josephine's Group in QA | Josephine's Group in QA | Jennifer Le @ SD; Stacy Wong @ PCI; Maedhbh Hanley @ Cork | Jennifer Le @ SD; Stacy Wong @ PCI; Maedhbh Hanley @ Cork |  | Jennifer Le @ SD; Stacy Wong @ PCI; Maedhbh Hanley @ Cork | Jennifer Le @ SD; Stacy Wong @ PCI; Maedhbh Hanley @ Cork |  | Jennifer Le @ SD; Stacy Wong @ PCI; Maedhbh Hanley @ Cork
Site | Production Line Number | PO Number | WO Number | Lot # | Lot Size | API Delivery | API Discharge | Fill Date | Unload Date and Capping | Sterility Samples pulled and start testing | Analytical Samples pull and ship | Analytical samples receipt | Visual inspection complete | Prep and arrange shipment | Ship under Q status and reciept at destination | Sterility testing and report | Final CMO batch record review / approval | Analytical testing completion and report | AO LIMS data entry | Concurrent batch record review | Gilead final batch record review and release Britestock | Receipt at Packaging Facility and Cork :ID testing | Destination: La Verne, PCI, Cork | Market: Clinical, EUA, Commercial | Labeling and packaging | Labeled/packaged product release | Targeted Release Date | Vial Qty to package | Days to Manufacture, package and fully release | PR# | Comments
GRO |  | Confirmed | CTM | EW2006A1 | 65377 |  |  | 2020-03-29 | 2020-04-02 | 2020-04-03 | 2020-04-02 | 2020-04-06 | 2020-04-13 | 2020-05-04 | 2020-05-07 | 2020-04-30 | 2020-05-02 | 2020-04-17 | 2020-05-01 | 2020-04-21 | 2020-05-01 | 2020-05-08 | PCI | EUA | 2020-05-09 | 2020-05-10 |  | 65267 | 38 |  | Ship lot 6 next week if released before lot 14, shipping Monday the 4th. Truck arriving 4MAY and arriving to PCI 5MAY
GRO |  | Confirmed | CTM | EW2008A1 | 66588 |  |  | 2020-04-03 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-18 | 2020-05-05 | 2020-05-08 | 2020-04-27 | 2020-05-03 | 2020-04-20 | 2020-04-29 | 2020-04-22 | 2020-05-02 | 2020-05-09 | PCI | EUA | 2020-05-10 | 2020-05-11 |  | 66588 | 34 |  | Plan to ship Monday, Shipping Tuesday May 5th. Picking up 5MAY and delivering to PCI by 6MAY
GRO |  | Confirmed | CTM | EW2010A1 | 66895 |  |  | 2020-04-09 | 2020-04-13 | 2020-04-14 | 2020-04-13 | 2020-04-14 | 2020-04-24 | 2020-05-06 | 2020-05-09 | 2020-04-30 | 2020-04-29 | 2020-04-24 | 2020-05-04 | 2020-04-23 | 2020-05-07 | 2020-05-10 | PCI | EUA | 2020-05-11 | 2020-05-12 |  | 66895 | 29 |  | ship in Q Tuesday next week, Shipping Tuesday May 5th. Needs to be moved to org 275, will be able to release 4MAY. Transactions 5MAY to ship 6MAY
GRO |  | Confirmed | CTM | EW2012A1 | 66991 |  |  | 2020-04-14 | 2020-04-18 | 2020-04-19 | 2020-04-19 | 2020-04-20 | 2020-04-29 | 2020-05-13 | 2020-05-14 | 2020-05-08 | 2020-05-04 | 2020-04-30 | 2020-05-12 | 2020-04-28 | 2020-05-12 | 2020-05-15 | PCI | EUA | 2020-05-16 | 2020-05-17 |  | 66991 | 29 |  | Impurity lot. Working to release by 12MAY. Tentative release 12MAY to arrive to PCI by 13MAY to begin packaging 15MAY; (5/14)delivering to PCI 14MAY
GRO |  | Confirmed | PV1 | EW2014A1 | 66789 |  |  | 2020-04-19 | 2020-04-23 | 2020-04-24 | 2020-04-23 | 2020-04-24 | 2020-05-04 | 2020-05-12 | 2020-05-13 | 2020-05-08 | 2020-05-09 | 2020-05-18 | 2020-05-18 | 2020-05-13 | 2020-05-30 | 2020-05-14 | PCI | EUA | 2020-05-15 | 2020-05-16 |  | 66789 | 23 |  | Ship to PCI 12MAY under Q; (5/14)delivered to PCI on 13MAY
GRO |  | Confirmed | PV2 | EW2016A1 | 68200 |  |  | 2020-04-24 | 2020-04-28 | 2020-04-29 | 2020-04-29 | 2020-04-30 | 2020-05-09 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-14 | 2020-05-22 | 2020-05-24 | 2020-05-15 | 2020-06-03 | 2020-05-14 | PCI | EUA | 2020-05-15 | 2020-05-16 |  | 68200 | 18 |  | Ship to PCI 12MAY under Q; (5/14)delivered to PCI on 13MAY
GRO |  | Confirmed | PV3 | EW2018A1 | 68200 |  |  | 2020-04-29 | 2020-05-03 | 2020-05-04 | 2020-05-04 | 2020-05-05 | 2020-05-14 | 2020-05-15 | 2020-05-18 | 2020-05-19 | 2020-05-19 | 2020-05-26 | 2020-05-28 | 2020-05-18 | 2020-06-06 | 2020-05-19 | PCI | EUA | 2020-05-20 | 2020-05-21 |  | 68200 | 18 |  | Ship to PCI 14MAY under Q; (5/14)Will remain at GRO until QA released - will not ship in Q
GRO |  | 801477426 | 275001276 |  | 68200 |  | 2020-06-01 | 2020-06-05 | 2020-06-08 | 2020-06-09 | 2020-06-09 | 2020-06-11 | 2020-06-19 | 2020-06-20 | 2020-06-23 | 2020-06-24 | 2020-06-24 | 2020-06-21 | 2020-06-25 | 2020-06-23 | 2020-06-29 | 2020-06-24 | PCI | EUA | 2020-06-25 | 2020-06-26 | 2020-06-26 | 68200 | 18 |  | Commercial Batches
GRO |  | 801477687 | 275001277 |  | 68200 |  | 2020-06-08 | 2020-06-12 | 2020-06-15 | 2020-06-16 | 2020-06-16 | 2020-06-18 | 2020-06-26 | 2020-06-27 | 2020-06-30 | 2020-07-01 | 2020-07-01 | 2020-06-28 | 2020-07-02 | 2020-06-30 | 2020-07-06 | 2020-07-01 | PCI |  | 2020-07-02 | 2020-07-03 | 2020-07-03 |  | 18 |  | Commercial Batches
GRO |  | 801477688 | 275001278 |  | 68200 |  | 2020-06-15 | 2020-06-12 | 2020-06-15 | 2020-06-16 | 2020-06-16 | 2020-06-18 | 2020-06-26 | 2020-06-27 | 2020-06-30 | 2020-07-01 | 2020-07-01 | 2020-06-28 | 2020-07-02 | 2020-06-30 | 2020-07-06 | 2020-07-01 | PCI |  | 2020-07-02 | 2020-07-03 | 2020-07-10 |  | 18 |  | Commercial Batches
GRO |  | 801477689 | 275001279 |  | 68200 |  | 2020-06-15 | 2020-06-19 | 2020-06-22 | 2020-06-23 | 2020-06-23 | 2020-06-25 | 2020-07-03 | 2020-07-04 | 2020-07-07 | 2020-07-08 | 2020-07-08 | 2020-07-05 | 2020-07-09 | 2020-07-07 | 2020-07-13 | 2020-07-08 | PCI |  | 2020-07-09 | 2020-07-10 | 2020-07-10 |  | 18 |  | PV#1 Commercial Batches
GRO |  | 801477690 | 275001280 |  | 68200 |  | 2020-06-22 | 2020-06-19 | 2020-06-22 | 2020-06-23 | 2020-06-23 | 2020-06-25 | 2020-07-03 | 2020-07-04 | 2020-07-07 | 2020-07-08 | 2020-07-08 | 2020-07-05 | 2020-07-09 | 2020-07-07 | 2020-07-13 | 2020-07-08 | PCI |  | 2020-07-09 | 2020-07-10 | 2020-07-17 |  | 18 |  | PV#2 Commercial Batches
GRO |  | 801477691 | 275001281 |  | 68200 |  | 2020-06-29 | 2020-06-26 | 2020-06-29 | 2020-06-30 | 2020-06-30 | 2020-07-02 | 2020-07-10 | 2020-07-11 | 2020-07-14 | 2020-07-15 | 2020-07-15 | 2020-07-12 | 2020-07-16 | 2020-07-14 | 2020-07-20 | 2020-07-15 | PCI |  | 2020-07-16 | 2020-07-17 | 2020-07-24 |  | 18 |  | Commercial Batches
GRO |  | 801477692 | 275001282 |  | 68200 |  | 2020-06-29 | 2020-06-26 | 2020-06-29 | 2020-06-30 | 2020-06-30 | 2020-07-02 | 2020-07-10 | 2020-07-11 | 2020-07-14 | 2020-07-15 | 2020-07-15 | 2020-07-12 | 2020-07-16 | 2020-07-14 | 2020-07-20 | 2020-07-15 | PCI |  | 2020-07-16 | 2020-07-17 | 2020-07-24 |  | 18 |  | PV#3 Commercial Batches
GRO |  | 801477693 | 275001283 |  | 68200 |  | 2020-07-06 | 2020-07-03 | 2020-07-06 | 2020-07-07 | 2020-07-07 | 2020-07-09 | 2020-07-17 | 2020-07-18 | 2020-07-21 | 2020-07-22 | 2020-07-22 | 2020-07-19 | 2020-07-23 | 2020-07-21 | 2020-07-27 | 2020-07-22 | PCI |  | 2020-07-23 | 2020-07-24 | 2020-07-31 |  | 18 |  | Commercial Batches
GRO |  | 801477694 | 275001284 |  | 68200 |  | 2020-07-13 | 2020-07-03 | 2020-07-06 | 2020-07-07 | 2020-07-07 | 2020-07-09 | 2020-07-17 | 2020-07-18 | 2020-07-21 | 2020-07-22 | 2020-07-22 | 2020-07-19 | 2020-07-23 | 2020-07-21 | 2020-07-27 | 2020-07-22 | PCI |  | 2020-07-23 | 2020-07-24 | 2020-08-07 |  | 18 |  | Commercial Batches
GRO |  | 801477695 | 275001285 |  | 68200 |  | 2020-07-20 | 2020-07-10 | 2020-07-13 | 2020-07-14 | 2020-07-14 | 2020-07-16 | 2020-07-24 | 2020-07-25 | 2020-07-28 | 2020-07-29 | 2020-07-29 | 2020-07-26 | 2020-07-30 | 2020-07-28 | 2020-08-03 | 2020-07-29 | PCI |  | 2020-07-30 | 2020-07-31 | 2020-08-14 |  | 18 |  | Commercial Batches
GRO |  | Planned |  |  | 68200 |  |  | 2020-07-10 | 2020-07-13 | 2020-07-14 | 2020-07-14 | 2020-07-16 | 2020-07-24 | 2020-07-25 | 2020-07-28 | 2020-07-29 | 2020-07-29 | 2020-07-26 | 2020-07-30 | 2020-07-28 | 2020-08-03 | 2020-07-29 | PCI |  | 2020-07-30 | 2020-07-31 |  |  | 18
GRO |  | Planned |  |  | 68200 |  |  | 2020-07-17 | 2020-07-20 | 2020-07-21 | 2020-07-21 | 2020-07-23 | 2020-07-31 | 2020-08-01 | 2020-08-04 | 2020-08-05 | 2020-08-05 | 2020-08-02 | 2020-08-06 | 2020-08-04 | 2020-08-10 | 2020-08-05 | PCI |  | 2020-08-06 | 2020-08-07 |  |  | 18
GRO |  | Planned |  |  | 68200 |  |  | 2020-07-23 | 2020-07-26 | 2020-07-27 | 2020-07-27 | 2020-07-29 | 2020-08-06 | 2020-08-07 | 2020-08-10 | 2020-08-11 | 2020-08-11 | 2020-08-08 | 2020-08-12 | 2020-08-10 | 2020-08-16 | 2020-08-11 | PCI |  | 2020-08-12 | 2020-08-13 |  |  | 18
GRO |  | Planned |  |  | 68200 |  |  | 2020-07-30 | 2020-08-02 | 2020-08-03 | 2020-08-03 | 2020-08-05 | 2020-08-13 | 2020-08-14 | 2020-08-17 | 2020-08-18 | 2020-08-18 | 2020-08-15 | 2020-08-19 | 2020-08-17 | 2020-08-23 | 2020-08-18 | PCI |  | 2020-08-19 | 2020-08-20 |  |  | 18
GRO |  | Planned |  |  | 68200 |  |  | 2020-07-30 | 2020-08-02 | 2020-08-03 | 2020-08-03 | 2020-08-05 | 2020-08-13 | 2020-08-14 | 2020-08-17 | 2020-08-18 | 2020-08-18 | 2020-08-15 | 2020-08-19 | 2020-08-17 | 2020-08-23 | 2020-08-18 | PCI |  | 2020-08-19 | 2020-08-20 |  |  | 18
GRO |  | Planned |  |  | 68200 |  |  | 2020-08-21 | 2020-08-24 | 2020-08-25 | 2020-08-25 | 2020-08-27 | 2020-09-04 | 2020-09-05 | 2020-09-08 | 2020-09-09 | 2020-09-09 | 2020-09-06 | 2020-09-10 | 2020-09-08 | 2020-09-14 | 2020-09-09 | PCI |  | 2020-09-10 | 2020-09-11 |  |  | 18
GRO |  | Planned |  |  | 68200 |  |  | 2020-08-21 | 2020-08-24 | 2020-08-25 | 2020-08-25 | 2020-08-27 | 2020-09-04 | 2020-09-05 | 2020-09-08 | 2020-09-09 | 2020-09-09 | 2020-09-06 | 2020-09-10 | 2020-09-08 | 2020-09-14 | 2020-09-09 | PCI |  | 2020-09-10 | 2020-09-11 |  |  | 18
JHS | 1 | Confirmed |  | EW2005A1 | 17543 | on hand | consumed | 2020-03-27 |  |  | 2020-04-01 | 2020-04-02 |  | 2020-04-22 |  |  |  | 2020-04-10 | 2020-04-24 |  | 2020-04-20 | 2020-04-24 | La Verne | Clinical | 2020-04-27 | 2020-04-28 |  |  | 43949 |  | At SD
JHS | 1 | Confirmed |  | EW2007A1 | 22220.16 | on hand | consumed | 2020-04-02 | 2020-04-06 | 2020-04-09 | 2020-04-09 | 2020-04-10 | 2020-04-19 | 2020-04-23 | 2020-04-26 | 2020-04-23 | 2020-04-24 | 2020-04-21 | 2020-04-27 | 2020-04-18 | 2020-04-28 | 2020-04-24 | La Verne | Clinical | 2020-04-28 | 2020-04-30 |  |  | 24 |  | At SD
JHS | 1 | Confirmed |  | EW2009A1 | 15461 | on hand | consumed | 2020-04-07 | 2020-04-11 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-23 | 2020-04-29 | 2020-04-29 | 2020-04-29 | 2020-04-30 | 2020-04-23 | 2020-04-29 | 2020-04-22 | 2020-04-30 | 2020-04-30 | La Verne | Clinical | 2020-05-01 | 2020-05-02 | 2020-05-12 | 15472 | 21 |  | Split between clinical/Japan EUA - Clinical Portion; 2 open events (EET missing vial and shipper label with P/N translation)
JHS | 1 | Confirmed |  | EW2009A1 | 6600 | on hand | consumed | 2020-04-07 | 2020-04-11 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-23 | 2020-04-29 | 2020-04-29 | 2020-04-29 | 2020-04-30 | 2020-04-23 | 2020-04-29 | 2020-04-22 | 2020-04-30 | 2020-04-30 | La Verne | EUA | 2020-05-05 | 2020-05-06 | 2020-05-07 | 6600 | 25 |  | Split between clinical/Japan EUA - Japan EUA Portion - PKG 05-May
JHS | 1 | Confirmed |  | EW2011A1 | 22394.88 | on hand | consumed | 2020-04-09 | 2020-04-13 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-23 | 2020-04-24 | 2020-04-27 | 2020-04-27 | 2020-05-01 | 2020-04-23 | 2020-04-30 | 2020-04-29 | 2020-05-01 | 2020-05-15 | La Verne |  | 2020-05-16 | 2020-05-17 |  | 22779 | 34 |  | Ship wk of 4-May, releasing from JHS 01MAY ship to PCI. Working to ship 6MAY. Shipping lane needs to be setup in EBS to move to commercial org. Lot is on hold as of 5MAY. Most likely will ship to LV and package at LV. | EAU 330K
JHS | 1 | Confirmed |  | EW2013A1 | 22818 | on hand | consumed | 2020-04-14 | 2020-04-18 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-30 | 2020-05-08 | 2020-05-11 | 2020-05-04 | 2020-05-06 | 2020-05-01 | 2020-05-08 | 2020-05-05 | 2020-05-12 | 2020-05-12 | PCI |  | 2020-05-13 | 2020-05-14 |  |  | 26 |  | Q-Ship May 8, Mike to verify arrival date w/Jim and Stacy. Lot is on hold as of 5MAY. Most likely will ship and pack at LV. | EAU 330K
JHS | 1 | Confirmed |  | EW2015A1 | 22714 | on hand | consumed | 2020-04-22 | 2020-04-25 | 2020-04-27 | 2020-05-01 | 2020-05-02 | 2020-05-07 | 2020-05-08 | 2020-05-11 | 2020-05-16 | 2020-05-17 | 2020-05-12 | 2020-05-20 | 2020-05-15 | 2020-05-21 | 2020-05-12 | La Verne |  | 2020-05-13 | 2020-05-14 |  |  | 19 |  | Extended hold, may delay release. Ship to LV on 13MAY | EAU 330K
JHS | 1 | Confirmed | CTM | EW2017A1 | 22658 | on hand |  | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-30 | 2020-05-01 | 2020-05-08 | 2020-05-09 | 2020-05-12 | 2020-05-12 | 2020-05-15 | 2020-05-11 | 2020-05-13 | 2020-05-14 | 2020-05-16 | 2020-05-13 | La Verne |  | 2020-05-14 | 2020-05-15 |  |  | 18 |  | Ship to LV 13MAY
JHS | 1 | Confirmed | PV | EW2019A1 | 23328 | on hand |  | 2020-04-29 | 2020-05-02 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-14 | 2020-05-15 | 2020-05-18 | 2020-05-20 | 2020-05-20 | 2020-05-16 | 2020-05-20 | 2020-05-19 | 2020-05-24 | 2020-05-19 | La Verne |  | 2020-05-20 | 2020-05-21 |  |  | 19 |  | PR: chipped vial crowns. Impact to batch release is TBD.
JHS | 1 | Confirmed | PV | EW2020A1 | 23328 | on hand |  | 2020-05-18 | 2020-05-05 | 2020-05-06 | 2020-05-06 | 2020-05-08 | 2020-05-16 | 2020-05-17 | 2020-05-20 | 2020-05-20 | 2020-05-21 | 2020-05-18 | 2020-05-22 | 2020-05-20 | 2020-05-26 | 2020-05-21 | La Verne |  | 2020-05-22 | 2020-05-23 |  |  | 18 |  | This PV batch will be filled with Schott vials.
JHS | 1 | Confirmed | PV | EW2021A1 | 23328 | on hand |  | 2020-05-05 | 2020-05-09 | 2020-05-11 | 2020-05-10 | 2020-05-12 | 2020-05-21 | 2020-05-22 | 2020-05-25 | 2020-05-25 | 2020-05-26 | 2020-05-22 | 2020-05-28 | 2020-05-24 | 2020-05-31 | 2020-05-26 | La Verne |  | 2020-05-27 | 2020-05-28 |  |  | 19
JHS | 1 | 801477701 | 314000361 | C3000135 | 23328 |  |  | 2020-06-10 | 2020-06-13 | 2020-06-14 | 2020-06-14 | 2020-06-16 | 2020-06-24 | 2020-06-25 | 2020-06-28 | 2020-06-29 | 2020-06-29 | 2020-06-26 | 2020-06-30 | 2020-06-28 | 2020-07-04 | 2020-06-29 | La Verne |  | 2020-06-30 | 2020-07-01 |  |  | 18
JHS | 1 | 801477733 | 314000362 | C3000136 | 23328 |  |  | 2020-06-12 | 2020-06-15 | 2020-06-16 | 2020-06-16 | 2020-06-18 | 2020-06-26 | 2020-06-27 | 2020-06-30 | 2020-07-01 | 2020-07-01 | 2020-06-28 | 2020-07-02 | 2020-06-30 | 2020-07-06 | 2020-07-01 | La Verne |  | 2020-07-02 | 2020-07-03 |  |  | 18
JHS | 1 | 801477734 | 314000363 | C3000137 | 23328 |  |  | 2020-06-19 | 2020-06-22 | 2020-06-23 | 2020-06-23 | 2020-06-25 | 2020-07-03 | 2020-07-04 | 2020-07-07 | 2020-07-08 | 2020-07-08 | 2020-07-05 | 2020-07-09 | 2020-07-07 | 2020-07-13 | 2020-07-08 | La Verne |  | 2020-07-09 | 2020-07-10 |  |  | 18
JHS | 1 | 801477735 | 314000364 | C3000138 | 23328 |  |  | 2020-06-23 | 2020-06-26 | 2020-06-27 | 2020-06-27 | 2020-06-29 | 2020-07-07 | 2020-07-08 | 2020-07-11 | 2020-07-12 | 2020-07-12 | 2020-07-09 | 2020-07-13 | 2020-07-11 | 2020-07-17 | 2020-07-12 | La Verne |  | 2020-07-13 | 2020-07-14 |  |  | 18
JHS | 1 | 801477736 | 314000365 | C3000139 | 23328 |  |  | 2020-07-01 | 2020-07-04 | 2020-07-05 | 2020-07-05 | 2020-07-07 | 2020-07-15 | 2020-07-16 | 2020-07-19 | 2020-07-20 | 2020-07-20 | 2020-07-17 | 2020-07-21 | 2020-07-19 | 2020-07-25 | 2020-07-20 | La Verne |  | 2020-07-21 | 2020-07-22 |  |  | 18
JHS | 1 | 801477737 | 314000366 | C3000140 | 23328 |  |  | 2020-07-10 | 2020-07-13 | 2020-07-14 | 2020-07-14 | 2020-07-16 | 2020-07-24 | 2020-07-25 | 2020-07-28 | 2020-07-29 | 2020-07-29 | 2020-07-26 | 2020-07-30 | 2020-07-28 | 2020-08-03 | 2020-07-29 | La Verne |  | 2020-07-30 | 2020-07-31 |  |  | 18
JHS | 1 | 801477738 | 314000367 | C3000141 | 23328 |  |  | 2020-07-14 | 2020-07-17 | 2020-07-18 | 2020-07-18 | 2020-07-20 | 2020-07-28 | 2020-07-29 | 2020-08-01 | 2020-08-02 | 2020-08-02 | 2020-07-30 | 2020-08-03 | 2020-08-01 | 2020-08-07 | 2020-08-02 | La Verne |  | 2020-08-03 | 2020-08-04 |  |  | 18
JHS | 1 | 801477739 | 314000368 | C3000142 | 23328 |  |  | 2020-07-21 | 2020-07-24 | 2020-07-25 | 2020-07-25 | 2020-07-27 | 2020-08-04 | 2020-08-05 | 2020-08-08 | 2020-08-09 | 2020-08-09 | 2020-08-06 | 2020-08-10 | 2020-08-08 | 2020-08-14 | 2020-08-09 | La Verne |  | 2020-08-10 | 2020-08-11 |  |  | 18
JHS | 1 | 801477740 | 314000369 | C3000143 | 23328 |  |  | 2020-07-24 | 2020-07-27 | 2020-07-28 | 2020-07-28 | 2020-07-30 | 2020-08-07 | 2020-08-08 | 2020-08-11 | 2020-08-12 | 2020-08-12 | 2020-08-09 | 2020-08-13 | 2020-08-11 | 2020-08-17 | 2020-08-12 | La Verne |  | 2020-08-13 | 2020-08-14 |  |  | 18
JHS | 1 | 801477741 | 314000370 | C3000144 | 23328 |  |  | 2020-07-28 | 2020-07-31 | 2020-08-01 | 2020-08-01 | 2020-08-03 | 2020-08-11 | 2020-08-12 | 2020-08-15 | 2020-08-16 | 2020-08-16 | 2020-08-13 | 2020-08-17 | 2020-08-15 | 2020-08-21 | 2020-08-16 | La Verne |  | 2020-08-17 | 2020-08-18 |  |  | 18
JHS | 1 | 801477742 | 314000371 | C3000145 | 23328 |  |  | 2020-07-31 | 2020-08-03 | 2020-08-04 | 2020-08-04 | 2020-08-06 | 2020-08-14 | 2020-08-15 | 2020-08-18 | 2020-08-19 | 2020-08-19 | 2020-08-16 | 2020-08-20 | 2020-08-18 | 2020-08-24 | 2020-08-19 | La Verne |  | 2020-08-20 | 2020-08-21 |  |  | 18
JHS | 1 | 801477743 | 314000372 | C3000146 | 23328 |  |  | 2020-08-03 | 2020-08-06 | 2020-08-07 | 2020-08-07 | 2020-08-09 | 2020-08-17 | 2020-08-18 | 2020-08-21 | 2020-08-22 | 2020-08-22 | 2020-08-19 | 2020-08-23 | 2020-08-21 | 2020-08-27 | 2020-08-22 | La Verne |  | 2020-08-23 | 2020-08-24 |  |  | 18
JHS | 1 | Planned |  |  | 22154 |  |  | 2020-08-11 | 2020-08-14 | 2020-08-15 | 2020-08-15 | 2020-08-17 | 2020-08-25 | 2020-08-26 | 2020-08-29 | 2020-08-30 | 2020-08-30 | 2020-08-27 | 2020-08-31 | 2020-08-29 | 2020-09-04 | 2020-08-30 | La Verne |  | 2020-08-31 | 2020-09-01 |  |  | 18
JHS | 1 | Planned |  |  | 22154 |  |  | 2020-08-14 | 2020-08-17 | 2020-08-18 | 2020-08-18 | 2020-08-20 | 2020-08-28 | 2020-08-29 | 2020-09-01 | 2020-09-02 | 2020-09-02 | 2020-08-30 | 2020-09-03 | 2020-09-01 | 2020-09-07 | 2020-09-02 | La Verne |  | 2020-09-03 | 2020-09-04 |  |  | 18
Monza |  | Planned |  |  | 25000 |  |  | 2020-06-12 | 2020-06-15 | [7 empty] | 2020-06-30 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-06-19 | 2020-06-22 | [7 empty] | 2020-07-07 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-06-19 | 2020-06-22 | [7 empty] | 2020-07-07 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-06-26 | 2020-06-29 | [7 empty] | 2020-07-14 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-06-26 | 2020-06-29 | [7 empty] | 2020-07-14 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-07-03 | 2020-07-06 | [7 empty] | 2020-07-21 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-07-03 | 2020-07-06 | [7 empty] | 2020-07-21 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-07-10 | 2020-07-13 | [7 empty] | 2020-07-28 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-07-10 | 2020-07-13 | [7 empty] | 2020-07-28 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-08-07 | 2020-08-10 | [7 empty] | 2020-08-25 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-08-07 | 2020-08-10 | [7 empty] | 2020-08-25 |  | 1900-01-03 |  | 1900-01-09 | [9 empty] | 2
Monza |  | Planned |  |  | 25000 |  |  | 2020-08-14 | 2020-08-17 | [7 empty] | 2020-09-01 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-08-14 | 2020-08-17 | [7 empty] | 2020-09-01 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-08-21 | 2020-08-24 | [7 empty] | 2020-09-08 |  | 1900-01-03 |  | 1900-01-09
Monza |  | Planned |  |  | 25000 |  |  | 2020-08-21 | 2020-08-24 | [7 empty] | 2020-09-08 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-07-10 | 2020-07-13 | [7 empty] | 2020-07-28 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-07-17 | 2020-07-20 | [7 empty] | 2020-08-04 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-07-17 | 2020-07-20 | [7 empty] | 2020-08-04 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-07-24 | 2020-07-27 | [7 empty] | 2020-08-11 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-07-24 | 2020-07-27 | [7 empty] | 2020-08-11 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-07-24 | 2020-07-27 | [7 empty] | 2020-08-11 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-07 | 2020-08-10 | [7 empty] | 2020-08-25 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-07 | 2020-08-10 | [7 empty] | 2020-08-25 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-07 | 2020-08-10 | [7 empty] | 2020-08-25 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-14 | 2020-08-17 | [7 empty] | 2020-09-01 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-14 | 2020-08-17 | [7 empty] | 2020-09-01 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-14 | 2020-08-17 | [7 empty] | 2020-09-01 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-21 | 2020-08-24 | [7 empty] | 2020-09-08 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-21 | 2020-08-24 | [7 empty] | 2020-09-08 |  | 1900-01-03 |  | 1900-01-09
Pfizer McPherson |  | Planned |  |  | 45000 |  |  | 2020-08-21 | 2020-08-24 | [7 empty] | 2020-09-08 |  | 1900-01-03 |  | 1900-01-09
YaoPharma |  |  |  | 20260010 | 19221 |  |  | 2020-03-12 | 2020-03-15 | [7 empty] | 2020-03-30 |  | 1900-01-03 |  | 2020-06-03
YaoPharma |  |  |  | 20260020 |  |  |  | 2020-03-20 | 2020-03-23 | [7 empty] | 2020-04-07 |  | 1900-01-03 |  | 2020-05-19
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Xellia
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Fareva
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
Abbvie/Allergan
La Verne |  |  |  | 021266 | 24322 | [17 empty] | PCI | EUA |  |  | 2020-05-04
La Verne |  |  |  | 020952 | 24812 | [17 empty] | PCI | EUA |  | 2020-05-03 | 2020-05-03 | 24803
La Verne |  |  |  | 020953 | 21393 | [17 empty] | La Verne | EUA | 2020-05-04 | 2020-05-05 |  | 21348 |  |  | US EUA
La Verne |  |  |  | 020954 | 22279 | [17 empty] | La Verne | EUA | 2020-05-04 | 2020-05-05 |  | 22229 |  |  | US EUA
La Verne |  |  |  | 020955 | 22041 | [17 empty] | PCI | EUA |  |  | 2020-05-05
La Verne |  |  |  | 020956 | 23998 | [17 empty] | PCI | EUA |  |  | 2020-05-06
La Verne |  |  |  | 020957 | 24296 | [17 empty] | PCI | EUA |  |  | 2020-05-06
La Verne |  |  |  | 020958 | 398 | [14 empty] | 2020-05-07 | 2020-05-07 |  | La Verne
La Verne |  |  |  | 020959 | 24217 | [17 empty] | PCI | EUA | 2020-05-06 |  | 2020-05-07
La Verne |  |  |  | 020960 | 24434 | [17 empty] | La Verne | EUA | 2020-05-01 | 2020-05-02 |  | 24147 |  |  | US EUA
La Verne |  |  |  | 020961 | 24618 | [17 empty] | La Verne | EUA | 2020-05-02 | 2020-05-03 |  | 24520 |  |  | US EUA
La Verne |  |  |  | 020962 | 24690 | [17 empty] | La Verne | EUA | 2020-05-03 | 2020-05-03 |  | 24309 |  |  | US EUA
La Verne |  |  |  | 020963 | 23936.64 | [15 empty] | 2020-04-16 |  | La Verne | EUA | 2020-05-03 | 2020-05-04 |  | 23049 |  |  | US EUA
La Verne |  |  |  | 020951 | 23732.16 | [15 empty] | 2020-04-17 |  | PCI | EUA |  |  | 2020-05-08
La Verne |  |  |  | 020964 | 23637.12 | [15 empty] | 2020-04-18 |  | PCI | EUA |  |  | 2020-05-09
La Verne |  |  |  | 021393 | 23783 | [17 empty] | PCI |  |  |  | 2020-05-07
La Verne |  |  |  | 021525 | 23228.16 | [15 empty] | 2020-04-19 |  | PCI | EUA |  |  | 2020-05-10
La Verne |  |  |  | 021526 | 23521.92 | [15 empty] | 2020-04-20 |  | PCI |  |  |  | 2020-05-10 |  |  |  | Potentially shipping to PCI
|  |  | PV | EW2020A1
|  |  | PV | EW2021A1
Formulas:
Angela/Zong = +IF([Destination: La Verne, PCI, Cork]="Cork",[Angela/Zong]+8,[Angela/Zong]+10)
Angela/Zong = +[Angela/Zong]+R6
Jeff Perata and Angela/Zong for updates = +IF([Destination: La Verne, PCI, Cork]="Cork",[Jeff Perata and Angela/Zong for updates]+5,[Jeff Perata and Angela/Zong for updates]+3)
Jeff Perata and Angela/Zong for updates = +[Angela/Zong]+O6
Labeling and packaging = +IF([Destination: La Verne, PCI, Cork]="Cork",W9+2,W9+1)
Labeled/packaged product release = +[Labeling and packaging]+AA6
Josephine's Group in QA = +[Angela/Zong]+U6
Josephine's Group in QA = +[Angela/Zong]+V6
Garry/Quan = +[Angela/Zong]+M6
Garry/Quan = +[Garry/Quan]+S6

## Sheet2 (hidden)
Type |  | Disposition | Yield (vials) | Prod Year | Hyd Cal ID | Days from Today to Fill | FedEx PRO (SD to JHS) | Tank ID | IR/ISO (SD to JHS) | Gilead SD Bulk WO | Gilead Bulk Lot | JHS Lot | JHS Lyo Unit | JHS PO (ASN) | Gilead FC Service PO | Gilead FC Request Date | Gilead FC Subcon. WO | Prod Year | Gilead FC Outbound IR/ISO | Gilead SD Hydration Start Date | +/- | Gilead SD Bulk Liquid Ship | JHS Fill | Gilead FC Service PO | Target Ship BSTK from JHS | End of Hyd to Fill
Commercial | 1 | DELIVER ON FILL DATE |  | 2019 | JHS 1 | -489 |  |  |  | 100008949 | 015971 | D1900004 |  | 4100040429 |  |  |  | #N/A |  | 2019-01-13 |  | 2019-01-15 | 2019-01-16 |  | 2019-03-24 | -2
Commercial | 2 |  |  | 2019 | JHS 2 | -483 |  |  |  | 100008948 | 015970 | D1900003 |  | 4100040429 |  |  |  | #N/A |  | 2019-01-11 | 5 | 2019-01-18 | 2019-01-22 |  | 2019-03-30 | -10
Commercial | 3 | 015185 Replaced by 016101 |  | 2019 | JHS 3 | -480 |  |  |  | 100009036 | 016101 | D1900006 |  | 4100040429 |  |  |  | #N/A |  | 2019-01-18 | 3 | 2019-01-23 | 2019-01-25 |  | 2019-04-02 | -6
Commercial | 4 | same day delivery |  | 2019 | JHS 4 | -477 |  |  |  | 100008950 | 015972 | D1900063 |  | 4100040430 |  |  |  | #N/A |  | 2019-01-24 | 1 | 2019-01-27 | 2019-01-28 |  | 2019-04-05 | -3
Commercial | 5 |  |  | 2019 | JHS 5 | -475 |  |  |  | 100008951 | 015973 | D1900007 |  | 4100040429 |  |  |  | #N/A |  | 2019-01-26 |  | 2019-01-28 | 2019-01-30 |  | 2019-04-07 | -3
Commercial | 6 | switched with 015974 |  | 2019 | JHS 6 | -468 |  |  |  | 100009052 | 016310 | D1900009 |  | 4100040429 |  |  |  | #N/A |  | 2019-02-01 |  | 2019-02-03 | 2019-02-06 |  | 2019-04-14 | -4
Commercial | 7 | Switched with 015974 |  | 2019 | JHS 7 | -465 |  |  |  | 100009053 | 016311 | D1900010 |  | 4100040429 |  |  |  | #N/A |  | 2019-02-05 |  | 2019-02-07 | 2019-02-09 |  | 2019-04-17 | -3
Commercial | 8 |  |  | 2019 | JHS 8 | -461 |  |  |  | 100008952 | 015974 | D1900011 |  | 4100040429 |  |  |  | #N/A |  | 2019-02-08 | 1 | 2019-02-11 | 2019-02-13 |  | 2019-04-21 | -4
Commercial | 9 |  |  | 2019 | JHS 9 | -413 | [5 empty] | D1900013 | [5 empty] | #N/A |  | 2019-03-25 | 1 | 2019-03-28 | 2019-04-02 |  | 2019-06-08 | -7
Commercial | 10 |  |  | 2019 | JHS 10 | -410 | [5 empty] | D1900014 | [5 empty] | #N/A |  | 2019-03-28 | 3 | 2019-04-02 | 2019-04-05 |  | 2019-06-11 | -7
Commercial | 11 |  |  | 2019 | JHS 11 | -405 | [5 empty] | D1900015 | [5 empty] | #N/A |  | 2019-04-01 | 5 | 2019-04-08 | 2019-04-10 |  | 2019-06-16 | -8
Commercial | 12 |  |  | 2019 | JHS 12 | -399 | [5 empty] | D1900027 | [5 empty] | #N/A |  | 2019-04-05 | 1 | 2019-04-08 | 2019-04-16 |  | 2019-06-22 | -10
Commercial | 13 |  |  | 2019 | JHS 13 | -396 | [5 empty] | D1900028 | [5 empty] | #N/A |  | 2019-04-09 | 4 | 2019-04-15 | 2019-04-19 |  | 2019-06-25 | -9
Commercial | 14 |  |  | 2019 | JHS 14 | -391 | [5 empty] | D1900029 | [5 empty] | #N/A |  | 2019-04-15 | 5 | 2019-04-22 | 2019-04-24 |  | 2019-06-30 | -8
Commercial | 15 |  |  | 2019 | JHS 15 | -385 | [5 empty] | D1900030 | [5 empty] | #N/A |  | 2019-04-19 | 1 | 2019-04-22 | 2019-04-30 |  | 2019-07-06 | -10
Commercial | 16 |  |  | 2019 | JHS 16 | -382 | [11 empty] | #N/A |  | 2019-04-23 | 3 | 2019-04-28 | 2019-05-03 |  | 2019-07-09 | -9
Commercial | 17 |  |  | 2019 | JHS 17 | -377 | [11 empty] | #N/A |  | 2019-04-29 | 5 | 2019-05-06 | 2019-05-08 |  | 2019-07-14 | -8
Commercial | 18 |  |  | 2019 | JHS 18 | -371 | [11 empty] | #N/A |  | 2019-05-06 | 1 | 2019-05-09 | 2019-05-14 |  | 2019-07-20 | -7
Commercial | 19 |  |  | 2019 | JHS 19 | -368 | [11 empty] | #N/A |  | 2019-05-09 | 3 | 2019-05-14 | 2019-05-17 |  | 2019-07-23 | -7
Commercial | 20 |  |  | 2019 | JHS 20 | -363 | [11 empty] | #N/A |  | 2019-05-16 | 2 | 2019-05-20 | 2019-05-22 |  | 2019-07-28 | -5
Commercial | 21 |  |  | 2019 | JHS 21 | -354 | [11 empty] | #N/A |  | 2019-05-23 | 3 | 2019-05-28 | 2019-05-31 |  | 2019-08-06 | -7
Commercial | 22 |  |  | 2019 | JHS 22 | -349 | [11 empty] | #N/A |  | 2019-05-27 | 5 | 2019-06-03 | 2019-06-05 |  | 2019-08-11 | -8
Commercial | 23 |  |  | 2019 | JHS 23 | -343 | [11 empty] | #N/A |  | 2019-06-03 | 1 | 2019-06-06 | 2019-06-11 |  | 2019-08-17 | -7
Commercial | 24 |  |  | 2019 | JHS 24 | -340 | [11 empty] | #N/A |  | 2019-06-07 | 1 | 2019-06-10 | 2019-06-14 |  | 2019-08-20 | -6
Commercial | 25 |  |  | 2019 | JHS 25 | -335 | [11 empty] | #N/A |  | 2019-06-13 | 2 | 2019-06-17 | 2019-06-19 |  | 2019-08-25 | -5
Commercial | 26 |  |  | 2019 | JHS 26 | -329 | [11 empty] | #N/A |  | 2019-06-17 | 1 | 2019-06-20 | 2019-06-25 |  | 2019-08-31 | -7
Commercial | 27 |  |  | 2019 | JHS 27 | -326 | [11 empty] | #N/A |  | 2019-06-18 | 3 | 2019-06-23 | 2019-06-28 |  | 2019-09-03 | -9
Commercial | 28 |  |  | 2019 | JHS 28 | -321 | [11 empty] | #N/A |  | 2019-06-20 | 3 | 2019-06-25 | 2019-07-03 |  | 2019-09-08 | -12
Commercial | 29 |  |  | 2019 | JHS 29 | -298 | [11 empty] | #N/A |  | 2019-07-18 | 3 | 2019-07-23 | 2019-07-26 |  | 2019-10-01 | -7
Commercial | 30 |  |  | 2019 | JHS 30 | -293 | [11 empty] | #N/A |  | 2019-07-22 | 5 | 2019-07-29 | 2019-07-31 |  | 2019-10-06 | -8
Commercial | 31 |  |  | 2019 | JHS 31 | -287 | [11 empty] | #N/A |  | 2019-07-29 | 1 | 2019-08-01 | 2019-08-06 |  | 2019-10-12 | -7
Commercial | 32 |  |  | 2019 | JHS 32 | -284 | [11 empty] | #N/A |  | 2019-08-05 |  | 2019-08-07 | 2019-08-09 |  | 2019-10-15 | -3
Commercial | 33 |  |  | 2019 | JHS 33 | -279 | [11 empty] | #N/A |  | 2019-08-09 | 1 | 2019-08-12 | 2019-08-14 |  | 2019-10-20 | -4
Commercial | 34 |  |  | 2019 | JHS 34 | -273 | [11 empty] | #N/A |  | 2019-08-15 | 1 | 2019-08-18 | 2019-08-20 |  | 2019-10-26 | -4
Commercial | 35 |  |  | 2019 | JHS 35 | -244 | [11 empty] | #N/A |  | 2019-09-10 | 4 | 2019-09-16 | 2019-09-18 |  | 2019-11-24 | -7
Commercial | 36 |  |  | 2019 | JHS 36 | -238 | [11 empty] | #N/A |  | 2019-09-16 | 1 | 2019-09-19 | 2019-09-24 |  | 2019-11-30 | -7
Commercial | 37 |  |  | 2019 | JHS 37 | -235 | [11 empty] | #N/A |  | 2019-09-19 | 2 | 2019-09-23 | 2019-09-27 |  | 2019-12-03 | -7
Commercial | 38 |  |  | 2019 | JHS 38 | -230 | [11 empty] | #N/A |  | 2019-09-24 | 4 | 2019-09-30 | 2019-10-02 |  | 2019-12-08 | -7
Commercial | 39 |  |  | 2019 | JHS 39 | -224 | [11 empty] | #N/A |  | 2019-10-01 | 3 | 2019-10-06 | 2019-10-08 |  | 2019-12-14 | -6
Commercial | 40 |  |  | 2019 | JHS 40 | -221 | [11 empty] | #N/A |  | 2019-10-04 | 2 | 2019-10-08 | 2019-10-11 |  | 2019-12-17 | -6
Commercial | 41 |  |  | 2019 | JHS 41 | -216 | [11 empty] | #N/A |  | 2019-10-10 | 1 | 2019-10-13 | 2019-10-16 |  | 2019-12-22 | -5
Commercial | 42 |  |  | 2019 | JHS 42 | -210 | [11 empty] | #N/A |  | 2019-10-14 | 1 | 2019-10-17 | 2019-10-22 |  | 2019-12-28 | -7
Commercial | 43 |  |  | 2019 | JHS 43 | -207 | [11 empty] | #N/A |  | 2019-10-18 | 2 | 2019-10-22 | 2019-10-25 |  | 2019-12-31 | -6
Commercial | 44 |  |  | 2019 | JHS 44 | -202 | [11 empty] | #N/A |  | 2019-10-21 | 5 | 2019-10-28 | 2019-10-30 |  | 2020-01-05 | -8
Commercial | 45 |  |  | 2019 | JHS 45 | -196 | [11 empty] | #N/A |  | 2019-10-28 | 1 | 2019-10-31 | 2019-11-05 |  | 2020-01-11 | -7
Commercial | 46 |  |  | 2019 | JHS 46 | -193 | [11 empty] | #N/A |  | 2019-11-04 |  | 2019-11-06 | 2019-11-08 |  | 2020-01-14 | -3
Commercial | 47 |  |  | 2019 | JHS 47 | -188 | [11 empty] | #N/A |  | 2019-11-08 | 1 | 2019-11-11 | 2019-11-13 |  | 2020-01-19 | -4
Commercial | 48 |  |  | 2019 | JHS 48 | -182 | [11 empty] | #N/A |  | 2019-11-11 | 4 | 2019-11-17 | 2019-11-19 |  | 2020-01-25 | -7
Commercial | 49 |  |  | 2019 | JHS 49 | -179 | [11 empty] | #N/A |  | 2019-11-14 | 3 | 2019-11-19 | 2019-11-22 |  | 2020-01-28 | -7
Commercial | 50 |  |  | 2019 | JHS 50 | -174 | [11 empty] | #N/A |  | 2019-11-18 | 5 | 2019-11-25 | 2019-11-27 |  | 2020-02-02 | -8
Commercial | 51 |  |  | 2019 | JHS 51 | -168 | [11 empty] | #N/A |  | 2019-11-26 | 3 | 2019-12-01 | 2019-12-03 |  | 2020-02-08 | -6
Commercial | 52 |  |  | 2019 | JHS 52 | -165 | [11 empty] | #N/A |  | 2019-11-29 | 2 | 2019-12-03 | 2019-12-06 |  | 2020-02-11 | -6
Commercial | 53 |  |  | 2019 | JHS 53 | -160 | [11 empty] | #N/A |  | 2019-12-05 | 2 | 2019-12-09 | 2019-12-11 |  | 2020-02-16 | -5
Commercial | 54 |  |  | 2019 | JHS 54 | -154 | [11 empty] | #N/A |  | 2019-12-12 | 1 | 2019-12-15 | 2019-12-17 |  | 2020-02-22 | -4
Commercial | 55 |  |  | 2019 | JHS 55 | -151 | [11 empty] | #N/A |  | 2019-12-13 | 3 | 2019-12-18 | 2019-12-20 |  | 2020-02-25 | -6
Commercial | 1 | CANCELLED |  | 2019 | OSO 1 | -482 |  |  |  |  | INDEXED DOWN | [6 empty] | 2018 |  | 2019-01-23 |  | 2019-01-25 | 2019-01-23 |  |  |  | 1
Commercial | 2 |  |  | 2019 | OSO 2 | -479 |  |  |  | 100009020 | 016130 | GAD138 | [5 empty] | 2018 |  | 2019-01-20 |  | 2019-01-22 | 2019-01-26 |  |  |  | -5
Commercial | 3 |  |  | 2019 | OSO 3 | -477 |  |  |  | 100009022 | 016132 | GAD139 | [5 empty] | 2018 |  | 2019-01-22 |  | 2019-01-24 | 2019-01-28 |  |  |  | -5
Commercial | 4 | SAME DAY DELIVERY |  | 2019 | OSO 4 | -473 |  |  |  | 100009021 | 016131 | GAD140 | [5 empty] | 2018 |  | 2019-01-28 |  | 2019-01-30 | 2019-02-01 |  |  |  | -3
Commercial | 5 |  |  | 2019 | OSO 5 | -469 |  |  |  | 100009023 | 016133 | GAD141 | [5 empty] | 2018 |  | 2019-01-30 |  | 2019-02-01 | 2019-02-05 |  |  |  | -5
Commercial | 6 | SAME DAY DELIVERY |  | 2019 | OSO 6 | -466 |  |  |  | 100009024 | 016134 | GAD142 | [5 empty] | 2018 |  | 2019-02-04 |  | 2019-02-06 | 2019-02-08 |  |  |  | -3
Commercial | 7 | SAME DAY DELIVERY |  | 2019 | OSO 7 | -464 |  |  |  | 100009025 | 016135 | GAD143 | [5 empty] | 2018 |  | 2019-02-07 |  | 2019-02-09 | 2019-02-10 |  |  |  | -2
Commercial | 8 | SAME DAY DELIVERY |  | 2019 | OSO 8 | -460 |  |  |  | 100009026 | 016136 | GAD144 | [5 empty] | 2018 |  | 2019-02-11 |  | 2019-02-13 | 2019-02-14 |  |  |  | -2
Commercial | 9 |  |  | 2019 | OSO 9 | -458 |  |  |  | 100009093 | 016304 | GAD145 | [5 empty] | 2018 |  | 2019-02-12 |  | 2019-02-14 | 2019-02-16 |  |  |  | -3
Commercial | 10 |  |  | 2019 | OSO 10 | -455 |  |  |  | 100009094 | 016305 | GAD146 | [5 empty] | 2018 |  | 2019-02-15 |  | 2019-02-17 | 2019-02-19 |  |  |  | -3
Commercial | 11 | SAME DAY DELIVERY |  | 2019 | OSO 11 | -453 |  |  |  | 100009095 | 016306 | GAD147 | [5 empty] | 2018 |  | 2019-02-18 |  | 2019-02-20 | 2019-02-21 |  |  |  | -2
Commercial | 12 |  |  | 2019 | OSO 12 | -450 |  |  |  | 100009096 | 016393 | GAD148 | [5 empty] | 2018 |  | 2019-02-19 |  | 2019-02-21 | 2019-02-24 |  |  |  | -4
Commercial | 13 |  |  | 2019 | OSO 13 | -448 |  |  |  | 100009097 | 016394 | GAD149 | [5 empty] | 2018 |  | 2019-02-22 |  | 2019-02-24 | 2019-02-26 |  |  |  | -3
Commercial | 14 |  |  | 2019 | OSO 14 | -445 |  |  |  | 100009098 | 016395 | GAD150 | [5 empty] | 2018 |  | 2019-02-25 |  | 2019-02-27 | 2019-03-01 |  |  |  | -3
Commercial | 15 |  |  | 2019 | OSO 15 | -443 |  |  |  | 100009099 | 016396 | GAD151 | [5 empty] | 2018 |  | 2019-02-26 |  | 2019-02-28 | 2019-03-03 |  |  |  | -4
Commercial | 16 |  |  | 2019 | OSO 16 | -440 |  |  |  | 100009100 | 016397 | GAD152 | [5 empty] | 2018 |  | 2019-02-28 | 2 | 2019-03-04 | 2019-03-06 |  |  |  | -5
Commercial | 17 |  |  | 2019 | OSO 17 | -438 | [5 empty] | GAD153 | [5 empty] | 2018 |  | 2019-03-01 | 3 | 2019-03-06 | 2019-03-08 |  |  |  | -6
Commercial | 18 |  |  | 2019 | OSO 18 | -435 | [5 empty] | GAD154 | [5 empty] | 2018 |  | 2019-03-04 | 1 | 2019-03-07 | 2019-03-11 |  |  |  | -6
Commercial | 19 |  |  | 2019 | OSO 19 | -432 | [5 empty] | GAD155 | [5 empty] | 2018 |  | 2019-03-05 | 4 | 2019-03-11 | 2019-03-14 |  |  |  | -8
Commercial | 20 |  |  | 2019 | OSO 20 | -429 | [5 empty] | GAD156 | [5 empty] | 2018 |  | 2019-03-11 | 1 | 2019-03-14 | 2019-03-17 |  |  |  | -5
Commercial | 21 |  |  | 2019 | OSO 21 | -427 | [5 empty] | GAD157 | [5 empty] | 2018 |  | 2019-03-12 |  | 2019-03-14 | 2019-03-19 |  |  |  | -6
Commercial | 22 |  |  | 2019 | OSO 22 | -424 | [5 empty] | GAD158 | [5 empty] | 2018 |  | 2019-03-14 | 3 | 2019-03-19 | 2019-03-22 |  |  |  | -7
Commercial | 23 |  |  | 2019 | OSO 23 | -422 | [5 empty] | GAD159 | [5 empty] | 2018 |  | 2019-03-15 | 1 | 2019-03-18 | 2019-03-24 |  |  |  | -8
Commercial | 24 |  |  | 2019 | OSO 24 | -419 | [5 empty] | GAD160 | [5 empty] | 2018 |  | 2019-03-18 | 5 | 2019-03-25 | 2019-03-27 |  |  |  | -8
Commercial | 25 |  |  | 2019 | OSO 25 | -414 | [5 empty] | GAD161 | [5 empty] | 2018 |  | 2019-03-22 | 3 | 2019-03-27 | 2019-04-01 |  |  |  | -9
Commercial | 26 |  |  | 2019 | OSO 26 | -411 | [5 empty] | GAD162 | [5 empty] | #N/A |  | 2019-03-26 | 4 | 2019-04-01 | 2019-04-04 |  |  |  | -8
Commercial | 27 |  |  | 2019 | OSO 27 | -409 | [5 empty] | GAD163 | [5 empty] | 2018 |  | 2019-03-29 | 2 | 2019-04-02 | 2019-04-06 |  |  |  | -7
Commercial | 28 |  |  | 2019 | OSO 28 | -405 | [5 empty] | GAD164 | [5 empty] | #N/A |  | 2019-04-02 | 4 | 2019-04-08 | 2019-04-10 |  |  |  | -7
Commercial | 29 |  |  | 2019 | OSO 29 | -404 | [5 empty] | GAD165 | [5 empty] | #N/A |  | 2019-04-04 | 2 | 2019-04-08 | 2019-04-11 |  |  |  | -6
Commercial | 30 |  |  | 2019 | OSO 30 | -396 | [5 empty] | GAD166 | [5 empty] | 2018 |  | 2019-04-12 | 1 | 2019-04-15 | 2019-04-19 |  |  |  | -6
Commercial | 31 |  |  | 2019 | OSO 31 | -391 | [5 empty] | GAD167 | [5 empty] | #N/A |  | 2019-04-16 | 4 | 2019-04-22 | 2019-04-24 |  |  |  | -7
Commercial | 32 |  |  | 2019 | OSO 32 | -389 | [5 empty] | GAD168 | [5 empty] | 2018 |  | 2019-04-18 | 4 | 2019-04-24 | 2019-04-26 |  |  |  | -7
Commercial | 33 |  |  | 2019 | OSO 33 | -383 | [5 empty] | GAD169 | [5 empty] | 2018 |  | 2019-04-22 | 5 | 2019-04-29 | 2019-05-02 |  |  |  | -9
Commercial | 34 |  |  | 2019 | OSO 34 | -381 | [5 empty] | GAD170 | [5 empty] | 2018 |  | 2019-04-25 | 2 | 2019-04-29 | 2019-05-04 |  |  |  | -8
Commercial | 35 |  |  | 2019 | OSO 35 | -377 | [5 empty] | GAD171 | [5 empty] | #N/A |  | 2019-04-30 | 4 | 2019-05-06 | 2019-05-08 |  |  |  | -7
Commercial | 36 |  |  | 2019 | OSO 36 | -376 | [5 empty] | GAD172 | [5 empty] | 2018 |  | 2019-05-02 | 2 | 2019-05-06 | 2019-05-09 |  |  |  | -6
Commercial | 37 |  |  | 2019 | OSO 37 | -370 | [5 empty] | GAD173 | [5 empty] | 2018 |  | 2019-05-07 | 4 | 2019-05-13 | 2019-05-15 |  |  |  | -7
Commercial | 38 |  |  | 2019 | OSO 38 | -368 | [5 empty] | GAD174 | [5 empty] | 2018 |  | 2019-05-10 | 1 | 2019-05-13 | 2019-05-17 |  |  |  | -6
Commercial | 39 |  |  | 2019 | OSO 39 | -365 | [5 empty] | GAD175 | [5 empty] | 2018 |  | 2019-05-14 |  | 2019-05-16 | 2019-05-20 |  |  |  | -5
Commercial | 40 |  |  | 2019 | OSO 40 | -357 | [5 empty] | GAD176 | [5 empty] | 2018 |  | 2019-05-21 |  | 2019-05-23 | 2019-05-28 |  |  |  | -6
Commercial | 41 |  |  | 2019 | OSO 41 | -355 | [5 empty] | GAD177 | [5 empty] | 2018 |  | 2019-05-24 | 2 | 2019-05-28 | 2019-05-30 |  |  |  | -5
Commercial | 42 |  |  | 2019 | OSO 42 | -348 | [5 empty] | GAD178 | [5 empty] | 2018 |  | 2019-05-30 | 3 | 2019-06-04 | 2019-06-06 |  |  |  | -6
Commercial | 43 |  |  | 2019 | OSO 43 | -347 | [5 empty] | GAD179 | [5 empty] | 2018 |  | 2019-05-31 | 3 | 2019-06-05 | 2019-06-07 |  |  |  | -6
Commercial | 44 |  |  | 2019 | OSO 44 | -343 | [5 empty] | GAD180 | [5 empty] | 2018 |  | 2019-06-04 |  | 2019-06-06 | 2019-06-11 |  |  |  | -6
Commercial | 45 |  |  | 2019 | OSO 45 | -339 | [5 empty] | GAD181 | [5 empty] | 2018 |  | 2019-06-10 | 1 | 2019-06-13 | 2019-06-15 |  |  |  | -4
Commercial | 46 |  |  | 2019 | OSO 46 | -297 | [5 empty] | GAD182 | [5 empty] | 2018 |  | 2019-07-19 | 4 | 2019-07-25 | 2019-07-27 |  |  |  | -7
Commercial | 47 |  |  | 2019 | OSO 47 | -293 | [5 empty] | GAD183 | [5 empty] | 2018 |  | 2019-07-25 | 2 | 2019-07-29 | 2019-07-31 |  |  |  | -5
Commercial | 48 |  |  | 2019 | OSO 48 | -291 | [5 empty] | GAD184 | [5 empty] | 2018 |  | 2019-07-26 | 3 | 2019-07-31 | 2019-08-02 |  |  |  | -6
Commercial | 49 |  |  | 2019 | OSO 49 | -286 | [5 empty] | GAD185 | [5 empty] | 2018 |  | 2019-08-01 | 2 | 2019-08-05 | 2019-08-07 |  |  |  | -5
Commercial | 50 |  |  | 2019 | OSO 50 | -285 | [5 empty] | GAD186 | [5 empty] | 2018 |  | 2019-08-02 | 2 | 2019-08-06 | 2019-08-08 |  |  |  | -5
Commercial | 51 |  |  | 2019 | OSO 51 | -278 | [5 empty] | GAD187 | [5 empty] | 2018 |  | 2019-08-08 | 2 | 2019-08-12 | 2019-08-15 |  |  |  | -6
Commercial | 52 |  |  | 2019 | OSO 52 | -275 | [5 empty] | GAD188 | [5 empty] | 2018 |  | 2019-08-12 | 1 | 2019-08-15 | 2019-08-18 |  |  |  | -5
Commercial | 53 |  |  | 2019 | OSO 53 | -270 | [5 empty] | GAD189 | [5 empty] | 2018 |  | 2019-08-16 | 2 | 2019-08-20 | 2019-08-23 |  |  |  | -6
Commercial | 54 |  |  | 2019 | OSO 54 | -267 | [5 empty] | GAD190 | [5 empty] | 2018 |  | 2019-08-19 | 1 | 2019-08-22 | 2019-08-26 |  |  |  | -6
Commercial | 55 |  |  | 2019 | OSO 55 | -265 | [5 empty] | GAD191 | [5 empty] | 2018 |  | 2019-08-22 | 2 | 2019-08-26 | 2019-08-28 |  |  |  | -5
Commercial | 56 |  |  | 2019 | OSO 56 | -258 | [5 empty] | GAD192 | [5 empty] | 2018 |  | 2019-08-26 | 1 | 2019-08-29 | 2019-09-04 |  |  |  | -8
Commercial | 57 |  |  | 2019 | OSO 57 | -255 | [5 empty] | GAD193 | [5 empty] | 2018 |  | 2019-08-30 | 3 | 2019-09-04 | 2019-09-07 |  |  |  | -7
Commercial | 58 |  |  | 2019 | OSO 58 | -253 | [5 empty] | GAD194 | [5 empty] | 2018 |  | 2019-09-03 |  | 2019-09-05 | 2019-09-09 |  |  |  | -5
Commercial | 59 |  |  | 2019 | OSO 59 | -250 | [5 empty] | GAD195 | [5 empty] | #N/A |  | 2019-09-05 | 2 | 2019-09-09 | 2019-09-12 |  |  |  | -6
Commercial | 60 |  |  | 2019 | OSO 60 | -248 | [5 empty] | GAD196 | [5 empty] | #N/A |  | 2019-09-09 | 1 | 2019-09-12 | 2019-09-14 |  |  |  | -4
Commercial | 61 |  |  | 2019 | OSO 61 | -244 | [5 empty] | GAD197 | [5 empty] | #N/A |  | 2019-09-12 | 2 | 2019-09-16 | 2019-09-18 |  |  |  | -5
Commercial | 62 |  |  | 2019 | OSO 62 | -243 | [5 empty] | GAD198 | [5 empty] | #N/A |  | 2019-09-13 | 2 | 2019-09-17 | 2019-09-19 |  |  |  | -5
Commercial | 63 |  |  | 2019 | OSO 63 | -239 | [5 empty] | GAD199 | [5 empty] | #N/A |  | 2019-09-17 |  | 2019-09-19 | 2019-09-23 |  |  |  | -5
Commercial | 64 |  |  | 2019 | OSO 64 | -237 | [5 empty] | GAD200 | [5 empty] | #N/A |  | 2019-09-20 | 1 | 2019-09-23 | 2019-09-25 |  |  |  | -4
Commercial | 65 |  |  | 2019 | OSO 65 | -234 | [5 empty] | GAD201 | [5 empty] | #N/A |  | 2019-09-23 | 1 | 2019-09-26 | 2019-09-28 |  |  |  | -4
Commercial | 66 |  |  | 2019 | OSO 66 | -230 | [5 empty] | GAD202 | [5 empty] | #N/A |  | 2019-09-26 | 2 | 2019-09-30 | 2019-10-02 |  |  |  | -5
Commercial | 67 |  |  | 2019 | OSO 67 | -228 | [5 empty] | GAD203 | [5 empty] | #N/A |  | 2019-09-27 | 3 | 2019-10-02 | 2019-10-04 |  |  |  | -6
Commercial | 68 |  |  | 2019 | OSO 68 | -222 | [5 empty] | GAD204 | [5 empty] | #N/A |  | 2019-10-03 | 3 | 2019-10-08 | 2019-10-10 |  |  |  | -6
Commercial | 69 |  |  | 2019 | OSO 69 | -219 | [5 empty] | GAD205 | [5 empty] | #N/A |  | 2019-10-07 | 1 | 2019-10-10 | 2019-10-13 |  |  |  | -5
Commercial | 70 |  |  | 2019 | OSO 70 | -217 | [5 empty] | GAD206 | [5 empty] | #N/A |  | 2019-10-08 |  | 2019-10-10 | 2019-10-15 |  |  |  | -6
Commercial | 71 |  |  | 2019 | OSO 71 | -214 | [5 empty] | GAD207 | [5 empty] | #N/A |  | 2019-10-11 | 3 | 2019-10-16 | 2019-10-18 |  |  |  | -6
Commercial | 72 |  |  | 2019 | OSO 72 | -209 | [5 empty] | GAD208 | [5 empty] | #N/A |  | 2019-10-17 | 2 | 2019-10-21 | 2019-10-23 |  |  |  | -5
Commercial | 73 |  |  | 2019 | OSO 73 | -202 | [5 empty] | GAD209 | [5 empty] | #N/A |  | 2019-10-24 | 2 | 2019-10-28 | 2019-10-30 |  |  |  | -5
Commercial | 74 |  |  | 2019 | OSO 74 | -200 | [5 empty] | GAD210 | [5 empty] | #N/A |  | 2019-10-25 | 3 | 2019-10-30 | 2019-11-01 |  |  |  | -6
Commercial | 75 |  |  | 2019 | OSO 75 | -193 | [5 empty] | GAD211 | [5 empty] | #N/A |  | 2019-11-01 | 2 | 2019-11-05 | 2019-11-08 |  |  |  | -6
Commercial | 76 |  |  | 2019 | OSO 76 | -190 | [5 empty] | GAD212 | [5 empty] | #N/A |  | 2019-11-05 |  | 2019-11-07 | 2019-11-11 |  |  |  | -5
Commercial | 77 |  |  | 2019 | OSO 77 | -187 | [5 empty] | GAD213 | [5 empty] | #N/A |  | 2019-11-07 | 2 | 2019-11-11 | 2019-11-14 |  |  |  | -6
Commercial | 78 |  |  | 2019 | OSO 78 | -170 | [5 empty] | GAD214 | [5 empty] | #N/A |  | 2019-11-22 | 2 | 2019-11-26 | 2019-12-01 |  |  |  | -8
Commercial | 79 |  |  | 2019 | OSO 79 | -169 | [5 empty] | GAD215 | [5 empty] | #N/A |  | 2019-11-25 |  | 2019-11-27 | 2019-12-02 |  |  |  | -6
Commercial | 80 |  |  | 2019 | OSO 80 | -165 | [5 empty] | GAD216 | [5 empty] | #N/A |  | 2019-11-28 | 3 | 2019-12-03 | 2019-12-06 |  |  |  | -7
Formulas:
Days from Today to Fill = [JHS Fill]-TODAY()
Gilead SD Bulk Liquid Ship = IFERROR([Gilead SD Hydration Start Date]+2+V2,"")
Target Ship BSTK from JHS = [JHS Fill]+67
Note on X1: JHS Fill = Day 1